APPENDIX B-2 EVERSOURCE UNITIL VERSION PPA

DRAFT

OFFSHORE WIND GENERATION UNIT

POWER PURCHASE AGREEMENT

BETWEEN

[_________________]
[Buyer]

AND

[_________________]
[Seller]

As of [____________], 202_

TABLE OF CONTENTS

[TOC TO BE UPDATED]

Page

1.	DEFINITIONS	1

2.	EFFECTIVE DATE; TERM	15

2.1	Effective Date	15

2.2	Term	15

3.	FACILITY DEVELOPMENT AND OPERATION	15

3.1	Critical Milestones	15

3.2	Delay Damages	16

3.3	Construction and Changes in Capacity	17

3.4	Commercial Operation	18

3.5	Operation of the Facility	20

3.6	Interconnection and Delivery Services	23

4.	DELIVERY OF PRODUCTS	23

4.1	Obligation to Sell and Purchase Products	23

4.2	Scheduling and Delivery	24

4.3	Failure of Seller to Deliver Products	25

4.4	Failure by Buyer to Accept Delivery of Products	25

4.5	Delivery Point	25

4.6	Metering	25

4.7	RECs	27

4.8	Test Period	30

5.	PRICE AND PAYMENTS FOR PRODUCTS	30

5.1	Price for Products	30

5.2	Payment and Netting	31

5.3	Interest on Late Payment or Refund	32

5.4	Taxes, Fees and Levies	32

6.	SECURITY FOR PERFORMANCE 	34

6.1	Seller’s Support	34

6.2	Return of Credit Support	35

6.3	Buyer’s Rights and Remedies	35

7.	REPRESENTATIONS, WARRANTIES, COVENANTS AND ACKNOWLEDGEMENTS	40

7.1	Representations and Warranties of Buyer	40

7.2	Representations and Warranties of Seller	41

7.3	Continuing Nature of Representations and Warranties	44

8.	REGULATORY APPROVAL	44

8.1	Receipt of Regulatory Approval	44

8.2	Related Transmission Approvals	44

9.	BREACHES; REMEDIES	44

9.1	Events of Default by Either Party	44

9.2	Events of Default by Seller	45

9.3	Remedies	46

10.	FORCE MAJEURE	50

10.1	Force Majeure	50

11.	DISPUTE RESOLUTION	51

11.1	Dispute Resolution	51

11.2	Allocation of Dispute Costs	51

11.3	Consent to Jurisdiction	52

11.4	Waiver of Jury Trial and Inconvenient Forum Claim	52

12.	CONFIDENTIALITY	52

12.1	Nondisclosure	52

12.2	Public Statements	53

13.	INDEMNIFICATION	53

13.1	Indemnification Obligations	53

13.2	Failure to Defend	53

14.	ASSIGNMENT AND CHANGE OF CONTROL	53

14.1	Prohibition on Assignments	53

14.2	Permitted Assignment by Seller	53

14.3	Change in Control over Seller	53

14.4	Permitted Assignment by Buyer	54

14.5	Prohibited Assignments	54

15.	TITLE; RISK OF LOSS	54

16.	AUDIT	54

16.1	Audit	54

16.2	Access to Financial Information	54

17.	NOTICES	55

18.	WAIVER AND MODIFICATION	55

19.	INTERPRETATION	55

19.1	Choice of Law	55

19.2	Headings	55

19.3	Forward Contract	56

19.4	Standard of Review	56

19.5	Change in ISO-NE Rules and Practices	56

19.6	Dodd Frank Act Representations	56

19.7	Change in Law or Buyer’s Accounting Treatment, Subsequent Judicial or Regulatory Action	57

20.	COUNTERPARTS; FACSIMILE SIGNATURES	58

21.	NO DUTY TO THIRD PARTIES	58

22.	SEVERABILITY	58

23.	INDEPENDENT CONTRACTOR	58

24.	ENTIRE AGREEMENT	59

Exhibits

Exhibit A	Description of Facility
Exhibit B	Seller’s Critical Milestones – Permits and Real Estate Rights
Exhibit C	Form of Progress Report
Exhibit D	Products and Pricing
Exhibit E	Related Transmission Facilities
Exhibit F	Required Network Updates

Exhibit G	Form of Commitment Agreement

POWER PURCHASE AGREEMENT

This POWER PURCHASE AGREEMENT (as amended from time to time in accordance with the terms hereof, this “Agreement”) is entered into as of [_________], 20__ (the “Effective Date”), by and between [________________], a [__________________]  (“Buyer”), and [________________], a [__________________] (“Seller”).  Buyer and Seller are individually referred to herein as a “Party” and are collectively referred to herein as the “Parties”.

WHEREAS, Seller is developing the [_______] offshore wind electric generation facility to be located in [________],which is more fully described in Exhibit A hereto (the “Facility”), from which the Buyer’s Percentage Entitlement of the Products (as defined below) is to be delivered to Buyer pursuant to the terms of this Agreement; and

WHEREAS, subject to Section 4.1(b), the Facility is, and shall qualify as, a RPS Class I Renewable Generation Unit and as a Clean Peak Resource, and the Facility is eligible to satisfy the CES, and the Facility is expected to be in commercial operation by [_______] [not later than January 1, 2030]; and

WHEREAS, pursuant to Section 83C of the Green Communities Act as added by Chapter 188 of the Acts of 2016, An Act to Promote Energy Diversity (“Section 83C”) and pursuant to Section 21(a) of Chapter 227 of the Acts of 2018, Buyer is authorized to enter into certain long-term contracts for the purchase of energy or energy and renewable energy certificates from offshore wind generators meeting the requirements of Section 83C; and

WHEREAS, Buyer and Seller desire to enter into this Agreement whereby Buyer shall purchase from Seller certain [Energy] [Energy and RECs] [RECs] (each as defined herein) generated by or associated with the Facility;

NOW, THEREFORE, in consideration of the premises and of the mutual agreements contained herein, and for other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties hereby agree as follows:

DEFINITIONS

In addition to terms defined in the recitals hereto, the following terms shall have the meanings set forth below.  Any capitalized terms used in this Agreement and not defined herein shall have the same meaning as ascribed to such terms under the ISO-NE Practices and ISO-NE Rules.

“Actual Facility Size” shall mean the actual nameplate capacity of the Facility, as built, and as certified by an Independent Engineer, as provided in Section 3.4(b)(xv)(A), as may be increased pursuant to Section 3.3(b) and certified by an Independent Engineer in any Additional Construction IE Certificate delivered pursuant to Section 3.3(b).

“Additional Construction Certificates” shall mean, collectively, (a) the Additional Construction IE Certificate and (b) a Seller’s certification stating that (i) all of the conditions precedent set forth in Section 3.4(b) remain satisfied after giving effect to the portions of the Facility constructed during the Additional Construction Period and (ii) all requirements of the ISO-NE Rules and ISO-NE Practices for the delivery of the Products to Buyer have been satisfied.

“Additional Construction IE Certificate” shall mean an Independent Engineer’s certification stating (a) that (x) the portions of the Facility constructed during the Additional Construction Period have been completed in all material respects (excepting

punchlist items that do not affect the ability of the Facility and Network Upgrades, to operate as intended hereunder) in accordance with this Agreement and are capable of regular commercial operation in accordance with Good Utility Practice and the

manufacturer’s guidelines for all material components of the Facility and (y) all performance testing for such portions of the Facility has been successfully completed,

and (b) the Actual Facility Size as of such date.

“Additional Construction Period” shall have the meaning set forth in Section 3.3(b)

hereof.

“Adverse Determination” shall have the meaning set forth in Section 19.7(b) hereof.

“Affiliate” shall mean, with respect to any Person, any other Person that directly or indirectly through one or more intermediaries Controls, is Controlled by, or is under common Control with, such first Person.

“Agreement” shall have the meaning set forth in the first paragraph hereof.

“Alternative Compliance Payment Rate” shall mean the rate per MWh paid by electricity suppliers under applicable Law for failure to supply RECs in accordance with the RPS.

“Bid” shall mean the proposal submitted by Seller for the Facility in response to the Request for Proposals for Long-Term Contracts for Offshore Wind Energy Projects dated [_________], 2021 and issued by Buyer and other Massachusetts distribution companies.

“Business Day” shall mean a day on which Federal Reserve member banks in New York, New York are open for business; and a Business Day shall start at 8:00 a.m. and end at 5:00 p.m. Eastern Prevailing Time.

“Buyer” shall have the meaning set forth in the first paragraph hereof.

“Buyer’s Percentage Entitlement” shall mean Buyer’s rights to [________] percent ([__]%) of the Products.  Buyer’s Percentage Entitlement may be adjusted in accordance with Section 3.3(c).

“Buyer’s Taxes” shall have the meaning set forth in Section 5.4(a) hereof.

“Capacity Deficiency” shall mean, at the Commercial Operation Date the amount (expressed in MW), if any, by which the Actual Facility Size is less than the proposed nameplate capacity of the Facility as set forth in Exhibit A; provided, however, that the Commercial Operation Date shall not occur unless the Actual Facility Size as of the Commercial Operation Date is at least ninety percent (90%) of the proposed nameplate capacity of the Facility as set forth in Exhibit A.

“Catastrophic Failure” shall mean any failure of any piece of Key Equipment where (i) such failed Key Equipment has been maintained in accordance with Good Utility Practice and all other applicable requirements of this Agreement in all material respects, and (ii) such failure cannot reasonably be expected, in accordance with Good Utility Practice, to be corrected within three (3) months after the occurrence of such failure by Seller using commercially reasonable efforts in accordance with Good Utility Practice.

“Catastrophic Failure Period” shall mean (a) with respect to any Key Equipment described in clause (a) of such definition, eighteen (18) consecutive months after the twelve (12) month failure to produce Energy for Catastrophic Failure of transformers and (b) with respect to any other Key Equipment, twelve (12) consecutive months after the failure of such Key Equipment.

“CEA” shall have the meaning set forth in Section 19.6 hereof.

“Certificate” shall mean an electronic certificate created pursuant to the GIS Operating Rules or any successor thereto to represent certain Environmental Attributes of each MWh of Energy generated within the ISO-NE control area and the generation attributes of certain Energy imported into the ISO-NE control area.

“CES” shall mean the Clean Energy Standard requirements established pursuant to the regulations promulgated at 310 CMR 7.75 that require all retail electricity suppliers in Massachusetts to provide a minimum percentage of electricity from certain clean energy generating sources, and such successor laws and regulations as may be in effect from time to time.

“CFTC Rules” shall have the meaning set forth in Section 19.6 hereof.

“Clean Peak Energy Certificates” shall have the same meaning as in the GIS Operating Rules.

“Clean Peak Resource” shall have the same meaning as in Mass. Gen. Laws ch. 25A, Section 3 and 225 CMR 21.02, and such successor laws and regulations as may be in effect from time to time.

“Clean Peak Standard” shall mean the requirements established pursuant to Mass. Gen. Laws ch.25A, Section 17, 225 CMR 21.00 and any other regulations promulgated from time to time that require all retail electricity suppliers in Massachusetts to provide a minimum percentage of electricity from Clean Peak Resources, and such successor laws and regulations as may be in effect from time to time.

“Commercial Operation Date” shall mean the date on which the conditions set forth in Section 3.4(b) have been satisfied, as set out in a written notice from Seller to Buyer.

“Commitment Agreement” means that Commitment Agreement dated as of the date hereof by Seller for the benefit of Buyer, in the form attached hereto as Exhibit G, pursuant to which Seller agrees to negotiate in good faith and to use commercially reasonable efforts to enter into an agreement with any other owner or developer of an offshore wind generation facility that wishes to interconnect with the Related Transmission Facilities to be used by the Facility to Deliver Energy hereunder.

“Contract Maximum Amount” shall mean [___] MWh per hour of Energy and a corresponding portion of all other Products, as may be adjusted in accordance with Section 3.3(b).

“Contract Year” shall mean the twelve (12) consecutive calendar months starting on the first day of the calendar month following the Commercial Operation Date and each subsequent twelve (12) consecutive calendar month period; provided that the first Contract Year shall include the days in the prior month in which the Commercial Operation Date occurred.

“Control” or “Controlled” shall mean the possession, directly or indirectly, of the power to direct or cause the direction of the management and policies of a Person, whether through the ownership of voting securities, by contract or otherwise.

“Cover Damages” shall mean, with respect to any Delivery Failure, an amount equal to (a) the positive net amount, if, any, by which the Replacement Price exceeds the applicable Price that would have been paid for the Products pursuant to Section 5.1 hereof, multiplied by the quantity of that Delivery Failure, plus (b) any other costs incurred by Buyer in purchasing Replacement Energy and/or Replacement RECs due to that Delivery Failure, plus (c) any applicable penalties and other costs assessed by ISO-NE or any other Person against Buyer as a result of that Delivery Failure, plus (d) any other costs and losses incurred by Buyer as a result of that Delivery Failure.  Buyer shall provide a statement for the applicable period explaining in reasonable detail the calculation of any Cover Damages.

“Credit Support” shall mean collateral in the form of a letter of credit issued by a Qualified Bank in a form reasonably acceptable to Buyer.

“Critical Milestones” shall have the meaning set forth in Section 3.1 hereof.

“Day Ahead Energy Market” shall have the meaning set forth in the ISO-NE Rules.

“Default” shall mean any event or condition which, with the giving of notice or passage of time or both, could become an Event of Default.

“Defaulting Party” shall mean the Party with respect to which a Default or Event of Default has occurred.

“Delay Damages” shall mean the damages assessed pursuant to Section 3.2(a) hereof.

“Deliver” or “Delivery” shall mean with respect to (i) Energy, to supply Energy into Buyer’s ISO-NE account at the Delivery Point in accordance with the terms of this Agreement and the ISO-NE Rules, and (ii) RECs, to supply RECs in accordance with Section 4.7(e).

“Delivery Failure” shall have the meaning set forth in Section 4.3 hereof.

“Delivery Point” shall mean the specific location on the Pool Transmission Facilities where Seller shall Deliver its Energy to Buyer, as set forth in Exhibit A hereto.

“Development Period Security” shall have the meaning set forth in Section 6.1(a)  hereof.

“Dispute” shall have the meaning set forth in Section 11.1 hereof.

“DOER” shall mean the Massachusetts Department of Energy Resources and its successors.

“Eastern Prevailing Time” shall mean either Eastern Standard Time or Eastern Daylight Time, as in effect from time to time.

“Effective Date” shall have the meaning set forth in the first paragraph hereof.

“Energy” shall mean electric “energy,” as such term is defined in the ISO-NE Tariff, generated by the Facility as measured in MWh in Eastern Prevailing Time, less such Facility’s station service use, generator lead losses and transformer losses, which quantity for purposes of this Agreement will never be less than zero.

“Environmental Attributes” shall mean any and all attributes available under the ISO-NE Rules, the RPS, the Clean Peak Standard, the CES, the GWSA and under any and all other international, federal, regional, state or other law, rule, regulation, bylaw, treaty or other intergovernmental compact, decision, administrative decision, program (including any voluntary compliance or membership program), competitive market or business method (including all credits, certificates, benefits, and emission measurements, reductions, offsets and allowances and all other indicia of ownership or control related thereto) or otherwise that are attributable, now or in the future, to Buyer’s Percentage Entitlement to the favorable generation attributes or environmental attributes of the Facility or the Products produced by the Facility during the Services Term, up to and including the Contract Maximum Amount, including Buyer’s Percentage Entitlement to:  (a) any such credits, certificates, payments, benefits, offsets and allowances computed on the basis of the Facility’s generation using renewable technology or displacement of fossil-fuel derived or other conventional energy generation; (b) any Certificates (including without limitation Clean Peak Energy Certificates) issued pursuant to the GIS in connection with Energy generated by the Facility; and (c) any voluntary emission reduction credits obtained or obtainable by Seller in connection with the generation of Energy by the Facility; provided, however, that Environmental Attributes shall not in any event include: (i) any state or federal production tax credits; (ii) any state or federal investment tax credits or other tax credits associated with the construction or ownership of the Facility; or (iii) any state, federal or private grants, financing, guarantees or other credit support relating to the construction or ownership, operation or maintenance of the Facility or the output thereof.

“Event of Default” shall have the meaning set forth in Section 9.1 hereof and shall include the events and conditions described in Section 9.1 and Section 9.2 hereof.

“EWG” shall mean an exempt wholesale generator under 42 U.S.C. §§ 16451-16463, as amended from time to time, and FERC’s implementing regulations thereunder.

“Facility” shall have the meaning set forth in the Recitals.

“FCA” shall have the meaning set forth in Section 3.7 hereof.

“FCAQ” shall have the meaning set forth in Section 3.7 hereof.

“FERC” shall mean the United States Federal Energy Regulatory Commission, and shall include its successors.

“Financial Closing Date” shall mean the date of the closing of the agreements for Financing adequate for construction of the Facility and of an initial disbursement of funds under such agreements.

“Financing” shall mean any direct or indirect funding in connection with any development, bridge, construction, permanent debt or Tax Equity Transaction or refinancing for the Facility, including, without limitation, lease, inverted lease, sale-leaseback, partnership flip, monetization of tax benefits, back leverage financing, credit derivative arrangements, indebtedness, whether secured or unsecured, loans, guarantees, notes, convertible debt, and bond issuances.

“Force Majeure” shall have the meaning set forth in Section 10.1(a) hereof.

“Generation Unit” shall mean a facility that converts a fuel or an energy resource into electrical energy.

“GIS” shall mean the NEPOOL Generation Information System or any successor thereto, which includes a generation information database and certificate system, operated by NEPOOL, its designee or successor entity, that accounts for generation attributes of electricity generated or consumed within New England.

“GIS Operating Rules” are the NEPOOL Generation Information System Operating Rules effective as of the Effective Date, as amended, superseded, or restated from time to time.

“Good Utility Practice” shall mean compliance with all applicable laws, codes, rules and regulations, all ISO-NE Rules and ISO-NE Practices, and any practices, methods and acts engaged in or approved by a significant portion of the electric industry in New England during the relevant time period, or any of the practices, methods and acts which, in the exercise of reasonable judgment in light of the facts known at the time the decision is made, could have been expected to accomplish the desired result consistent with good business practices, reliability, safety and expedition.  Good Utility Practice is not intended to be limited to the optimum practice, method or act to the exclusion of all others, but rather is intended to include acceptable practices, methods and acts generally accepted in the electric industry in New England.

“Governmental Entity” shall mean any federal, state or local governmental agency, authority, department, instrumentality or regulatory body, and any court or tribunal, with jurisdiction over Seller, Buyer or the Facility.

“Guaranteed Commercial Operation Date” shall have the meaning set forth in Section 3.1(a)(viii) hereof.

“GWSA” shall mean the Massachusetts Global Warming Solutions Act (Mass.  Gen.  Laws ch. 298), and such successor laws and regulations as may be in effect from time to time.

“I.3.9 Confirmation” refers to the ISO-NE Tariff Section I.3.9 pertaining to ISO-NE’s approval of proposed plans as specified therein.

“Independent Engineer” shall mean a licensed professional engineer with expertise in the development of renewable energy projects using the same renewable energy technology as the Facility, reasonably selected by and retained by Seller in order to determine the as-built nameplate capacity of the Facility as provided in Section 3.4(b)(xv) hereof.

“Interconnecting Utility” shall mean the utility (which may or may not be Buyer or an Affiliate of Buyer) providing interconnection service for the Facility to the Transmission System of that utility.

“Interconnection Agreement” shall mean an agreement between Seller and the Interconnecting Utility and ISO-NE, as applicable, regarding the interconnection of the Facility to the Transmission System of the Interconnecting Utility, as the same may be amended from time to time.

“Interconnection Point” shall have the meaning set forth in the Interconnection Agreement.

“Internal Bilateral Transaction” shall mean an “Internal Bilateral for Market for Energy” as defined in the ISO-NE Tariff.

“ISO” or “ISO-NE” shall mean ISO New England Inc., the independent system operator established in accordance with the RTO arrangements for New England, or its successor.

“ISO-NE Practices” shall mean the ISO-NE practices and procedures for delivery and transmission of energy in effect from time to time and shall include, without limitation, applicable requirements of the NEPOOL Agreement, and any applicable successor practices and procedures.

“ISO-NE Rules” shall mean all rules and procedures adopted by NEPOOL, ISO-NE, or the RTO, and governing wholesale power markets and transmission in New England, as such rules may be amended from time to time, including but not limited to, the ISO-NE Tariff, the ISO-NE Operating Procedures (as defined in the ISO-NE Tariff), the ISO-NE Planning Procedures (as defined in the ISO-NE Tariff), the Transmission Operating Agreement (as defined in the ISO-NE Tariff), the ISO-NE Participants Agreement, the manuals, procedures and business process documents published by ISO-NE via its web site and/or by its e-mail distribution to appropriate NEPOOL participants and/or NEPOOL committees, as amended, superseded or restated from time to time.

“ISO-NE Tariff” shall mean ISO-NE’s Transmission, Markets and Services Tariff, FERC Electric Tariff No. 3, as amended, superseded or restated from time to time.

“ISO Settlement Market System” shall have the meaning as set forth in the ISO-NE Tariff.

“Key Equipment” shall mean any of the following pieces of equipment included in the Facility (a) the generator step-up transformers at the offshore substation and the transformers at the onshore substation, each as identified on Exhibit A, (b) the metal-clad switchgear, (c) the main circuit breaker, (d) the export cable or (e) the offshore substation.

“Late Payment Rate” shall have the meaning set forth in Section 5.3 hereof.

“Law” shall mean all federal, state and local statutes, regulations, rules, orders, executive orders, decrees, policies, judicial decisions and notifications.

“Lender” shall mean a party providing Financing for the development, construction or ownership of the Facility, or any refinancing of that Financing, and receiving a security interest in the Facility, and shall include hedge providers and any assignee or transferee of such a party and any trustee, collateral agent or similar entity acting on behalf of such a party.

“Locational Marginal Price” or “LMP” shall have the meaning set forth in the ISO-NE Rules.

“Marginal Loss Revenue Fund” shall have the meaning set forth in the ISO-NE Rules.

“Market Price” shall mean the price received by Buyer by selling the Energy into either the ISO-NE-administered Day Ahead or Real Time Markets, as applicable.

“MDPU” shall mean the Massachusetts Department of Public Utilities and its successors.

“Meters” shall have the meaning set forth in Section 4.6(a) hereof.

“Moody’s” shall mean Moody’s Investors Service, Inc., and any successor thereto.

“MW” shall mean a megawatt AC.

“MWh” shall mean a megawatt-hour (one MWh shall equal 1,000 kWh).

“NEPOOL” shall mean the New England Power Pool and any successor organization.

“NERC” shall mean the North American Electric Reliability Corporation and shall include any successor thereto.

“Network Upgrades” shall mean upgrades to the Pool Transmission Facilities and all Transmission Providers’ transmission and distribution systems, as determined and identified in the interconnection study approved in connection with construction of the Facility, necessary for Delivery of the Energy to the Delivery Point, including those that are necessary for Seller’s satisfaction of the obligations under Sections 3.6(a) and 3.7 of this Agreement and those that are included in Exhibit F.

“Node” shall have the meaning set forth in ISO-NE Rules.

“Non-Defaulting Party” shall mean the Party with respect to which a Default or Event of Default has not occurred.

“Operating Period Security” shall have the meaning set forth in Section 6.1(b) hereof.

“Party” and “Parties” shall have the meaning set forth in the first paragraph hereof.

“Permits” shall mean any permit, authorization, license, order, consent, waiver, exception, exemption, variance or other approval by or from, and any filing, report, certification, declaration, notice or submission to or with, any Governmental Entity required to authorize action, including any of the foregoing relating to the ownership, siting, construction, operation, use or maintenance of the Facility under any applicable Law and the Delivery of the Products in accordance with this Agreement.

“Person” shall mean an individual, partnership, corporation, limited liability company, limited liability partnership, limited partnership, association, trust, unincorporated organization, or a government authority or agency or political subdivision thereof.

“Pool Transmission Facilities” has the meaning given that term in the ISO-NE Rules.

“Power Cost Reconciliation Tariff” shall mean a fully reconciling cost recovery tariff mechanism that authorizes the establishment of a distribution charge that fully recovers Buyer’s net costs under this Agreement (including annual remuneration of up to two and three-quarters percent (2.75%)).  The rate reconciliation shall be designed in such a way as to limit the build-up of any under or over-recoveries over the course of the year.  A reconciliation shall occur at least annually, but may also be reconciled quarterly or monthly, to the extent necessary to eliminate regulatory lag for the recovery of costs or crediting of over-recoveries to customers.

“Price” shall mean the purchase price(s) for Products referenced in Section 5.1 hereof and set forth on Exhibit D.

“Products” shall mean [RECs] [Energy] [Energy and RECs]; provided, however, that [RECs][Energy] [Energy and RECs] generated by or associated with the Facility during the Test Period or in excess of the Contract Maximum Amount shall not be deemed Products.

“Purchased Power Accounting Authorization” shall mean authorization for Buyer, at Buyer’s sole discretion, to take appropriate steps to assure avoidance of a material, negative balance sheet impact on Buyer or Buyer’s direct or indirect parent company, upon appropriate filing with and approval by the MDPU; provided that such Purchased Power Accounting Authorization shall not impact Buyer’s obligation to purchase the Products under this Agreement or the Price Buyer pays for such Products.

“QF” shall mean a cogeneration or small power production facility which meets the criteria as defined by FERC in Title 18, Code of Federal Regulations, §§ 292.201 through 292.207, as amended from time to time.

“Qualified Bank” shall mean a U.S. commercial bank or the U.S. branch office of a foreign bank, in either case having (x) assets on its most recent audited balance sheet of at least $10,000,000,000 and (y) a rating for its senior long-term unsecured debt obligations of at least (A) “A-” by S&P and “A3” by Moody’s, if such entity is rated by both S&P and Moody’s or (B) “A-” by S&P or “A3” by Moody’s, if such entity is rated by either S&P or Moody’s but not both.

“Real Time Energy Market” shall have the meaning as set forth in the ISO-NE Rules.

“RECs” shall mean all of the Certificates (including without limitation Clean Peak Energy Certificates) and any and all other Environmental Attributes associated with the Energy or otherwise produced by the Facility including, but not limited to, those which satisfy the RPS for a RPS Class I Renewable Generation Unit, the Clean Peak Standard and the CES, and shall represent title to and claim over all such Environmental Attributes associated with the specified MWh of generation from the Facility.

“Regulatory Approval” shall mean the MDPU approval of this entire Agreement (including any amendment of this Agreement as provided for herein), which approval shall include without limitation:  (1) confirmation that this Agreement has been approved under Section 83C and the regulations promulgated thereunder and that all of the terms of such Section 83C and such regulations apply to this Agreement; (2) definitive regulatory authorization for Buyer to recover all of its costs incurred under and in connection with this Agreement for the entire term of this Agreement through the implementation of a Power Cost Reconciliation Tariff and/or other cost recovery or reconciliation mechanisms; (3) definitive regulatory authorization for Buyer to recover remuneration of up to two and three-quarters percent (2.75%) of Buyer’s annual payments under this Agreement for the term of this Agreement through the Power Cost Reconciliation Tariff; and (4) approval of any Purchased Power Accounting Authorization requested by Buyer in connection with the Regulatory Approval.  Such approval, confirmation and authorizations shall be acceptable in form and substance to Buyer in its sole discretion, shall not include any conditions or modifications that Buyer deems, in its sole discretion, to be unacceptable and shall be final and not subject to appeal or rehearing.

“Rejected Purchase” shall have the meaning set forth in Section 4.4 hereof.

“Related Transmission Approvals” shall mean those FERC filings, agreements, tariffs and approvals associated with service on the Related Transmission Facilities.

“Related Transmission Facilities” shall mean all facilities and equipment located between Seller’s Generation Unit collector system step-up transformers and the point of change of ownership at the onshore interconnection, including any modification, addition, or upgrades to such facilities and equipment, constructed to physically and electrically interconnect Seller’s Generation Units to the onshore transmission system, as described in Exhibit E hereto.

“Reliability Curtailment” shall mean any curtailment of Delivery of Energy resulting from (i) an emergency condition as defined in the Interconnection Agreement or the ISO-NE Tariff, or (ii) any other order or directive of the Interconnecting Utility or the Transmission Provider pursuant to an Interconnection Agreement or tariff.

“Replacement Energy” shall mean energy purchased by Buyer as replacement for any Delivery Failure relating to the Energy to be provided hereunder.

“Replacement Price” shall mean (A) the price at which Buyer, acting in a commercially reasonable manner, purchases Replacement Energy and Replacement RECs; provided, however, that in no event shall Buyer be required to utilize or change its utilization of its owned or controlled assets, contracts or market positions to minimize Seller’s liability, or (B) if Buyer elects in its sole discretion not to purchase Replacement Energy and/or Replacement RECs, the market value of energy and the Alternative Compliance Payment Rate as of the date and the time of the Delivery Failure. [Definition to be adjusted to reflect Products being sold]

“Replacement RECs” shall mean any generation or environmental attributes, including any Certificates or other certificates or credits related thereto reflecting generation by a RPS Class I Renewable Generation Unit and a generating facility eligible to satisfy the CES and the Clean Peak Standard (subject to Section 4.1(b)), generating the same Environmental Attributes as are expected to be generated by the Facility at such time, that are available for purchase by Buyer as replacement for any RECs not Delivered as required hereunder during the Services Term.

“Reporting Party” shall have the meaning set forth in Section 19.6(g) hereof.

“Resale Damages” shall mean, with respect to any Rejected Purchase, an amount equal to (a) the positive net amount, if any, by which the applicable Price that would have been paid pursuant to Section 5.1 hereof for such Rejected Purchase, had it been accepted, exceeds the Resale Price multiplied by the quantity of that Rejected Purchase (in MWh and/or RECs, as applicable), plus (b) any applicable penalties assessed by ISO-NE or any other Person against Seller as a result of Buyer’s failure to accept such Products in accordance with the terms of this Agreement, plus (c) transaction and other administrative costs reasonably incurred by Seller in re-selling such Rejected Purchase that Seller would not have incurred but for the Rejected Purchase.  Seller shall provide a written statement for the applicable period explaining in reasonable detail the calculation of any Resale Damages.

“Resale Price” shall mean the price at which Seller, acting in a commercially reasonable manner, sells or is paid for a Rejected Purchase; provided, however, that in no event shall Seller be required to utilize or change its utilization of the Facility or its other assets, contracts or market positions in order to minimize Buyer’s liability for such Rejected Purchase.

“RPS” shall mean the requirements established pursuant to Mass. Gen. Laws ch.25A, Section 11F and the regulations promulgated thereunder that require all retail electricity suppliers in Massachusetts to provide a minimum percentage of electricity from RPS Class I Renewable Generation Units, and such successor laws and regulations as may be in effect from time to time.

“RPS Class I Renewable Generation Unit” shall mean a Generation Unit termed a New Renewable Generation Unit in a Statement of Qualification issued by the DOER pursuant to 225 CMR 14.00.

“RTO” shall mean ISO-NE and any successor organization or entity to ISO-NE, as authorized by FERC to exercise the functions pursuant to FERC’s Order No. 2000 and FERC’s corresponding regulations, or any successor organization, or any other entity authorized to exercise comparable functions in subsequent orders or regulations of FERC.

“S&P” shall mean Standard & Poor’s Financial Services LLC, and any successor thereto.

“Schedule” or “Scheduling” shall mean the actions of Seller and/or its designated representatives pursuant to Section 4.2, of notifying, requesting and confirming to ISO-NE the quantity of Energy to be delivered on any given day or days (or in any given hour or hours) during the Services Term at the Delivery Point.

“Section 83C” shall have the meaning set forth in the recitals hereof.

“Seller” shall have the meaning set forth in the first paragraph hereof.

“Seller’s Taxes” shall have the meaning set forth in Section 5.4(a) hereof.

“Services Term” shall have the meaning set forth in Section 2.2(b) hereof.

“Statement of Qualification” shall mean a written document from the DOER that qualifies a Generation Unit as an RPS Class I Renewable Generation Unit, or that qualifies a portion of the annual electrical energy output of a Generation Unit as RPS Class I Renewable Generation (as defined in 225 CMR 14.02).

“Tax Equity Transaction” shall mean, with respect to Seller, any transaction or series of transactions pursuant to which (i) a Person either (A) obtains less than one hundred percent (100%) of the equity interests in Seller or any entity that has an interest in Seller in connection with a partnership flip transaction or (B) obtains all of the equity interests in Seller in connection with a lease, inverted lease or sale leaseback transaction (in either case, such Person, a “Tax Equity Investor”), (ii) such transaction or series of transactions does not result in a change in Control of Seller, subject to the Tax Equity Investor’s right to vote in any major decision with respect to Seller, and (iii) Seller retains control of the Facility.

“Term” shall have the meaning set forth in Section 2.2(a) hereof.

“Termination Payment” shall have the meaning set forth in Section 9.3(b) hereof.

“Test Period” shall have the meaning set forth in Section 3.4(a) hereof.

“Transmission Provider” shall mean (a) ISO-NE, its respective successor or Affiliates; (b) Buyer; and/or (c) such other third parties from whom transmission services are necessary for Seller to fulfill its performance obligations to Buyer hereunder, as the context requires.

“Transmission System” shall mean the transmission facilities operated by a Transmission Provider, now or hereafter in existence, which provide energy transmission service for the Energy to the point of change of ownership at the onshore interconnection.

“Unit Contingent” shall mean that the Products are to be supplied only from the Facility and only to the extent that the Facility is generating Energy.

EFFECTIVE DATE; TERM

Effective Date.  Subject in all respects to Article 8, this Agreement is effective as of the Effective Date.

Term.

The “Term” of this Agreement is the period beginning on the Effective Date and ending upon the final settlement of all obligations hereunder after the expiration of the Services Term or the earlier termination of this Agreement in accordance with its terms.

The “Services Term” is the period during which Buyer is obligated to purchase Products Delivered to Buyer by Seller commencing on the Commercial Operation Date and continuing for a period of [15 to 20] years from the Commercial Operation Date, unless this Agreement is earlier terminated in accordance with the provisions hereof.

At the expiration of the Term or earlier termination of this Agreement pursuant to the terms hereof, the Parties shall no longer be bound by the terms and provisions hereof, except (i) to the extent necessary to make payments of any amounts owed to the other Party arising prior to or resulting from termination of, or on account of a breach of, this Agreement, (ii) to the extent necessary to enforce the rights and the obligations of the Parties arising under this Agreement before such expiration or termination, and (iii) the obligations of the Parties hereunder with respect to confidentiality and indemnification shall survive the expiration or termination of this Agreement.

FACILITY DEVELOPMENT AND OPERATION

Critical Milestones.

Subject to the provisions of Section 3.1(d), commencing on the Effective Date, Seller shall develop the Facility in order to achieve the following milestones (“Critical Milestones”) on or before the dates set forth in this Section 3.1(a):

receipt of all necessary approvals by [____________] [relevant siting authorities for construction and operation of the Facility, the interconnection of the Facility to the Interconnecting Utility and the construction of Network Upgrades], in final form,  by [____________];

qualification determination notification under ISO-NE Tariff Section III.13.1.1.2.8 with respect to the New Generating Capacity Resource’s participation in the Forward Capacity Auction, stating summer and winter qualified capacity and a list of transmission upgrades required, if any, by [____________];

receipt of all Permits necessary to construct the Facility, as set forth in Exhibit B, in final form, by [_________];

acquisition of all required real property rights in addition to the federal lease referenced in Section 7.2(m) necessary for construction and operation of the Facility, the interconnection of the Facility to the Interconnecting Utility and the construction of Network Upgrades in full and final form with all options and/or contingencies having been exercised demonstrating complete site control as set forth in Exhibit B, by [_________];

the achievement of the Financial Closing Date or other demonstration to Buyer’s satisfaction of the financial capability of Seller to construct the Facility, including, as applicable, Seller’s financial obligations with respect to interconnection of the Facility to the Interconnecting Utility and construction of the Network Upgrades by [__________];

issuance of a full notice to proceed by Seller to its general contractor and commencement of construction of the Facility by [__________];

receipt of all Permits necessary to operate the Facility, as set forth in Exhibit B, in final form, by [_________]; and

achievement of the Commercial Operation Date by [___________] (“Guaranteed Commercial Operation Date”).

Seller shall provide Buyer with written notice of the achievement of each Critical Milestone within seven (7) days after that achievement, which notice shall include information demonstrating with reasonable specificity that such Critical Milestone has been achieved.  Seller acknowledges that Buyer will receive such notice solely to monitor progress toward the Commercial Operation Date, and Buyer shall have no responsibility or liability for the development, construction, operation or maintenance of the Facility.

Seller may elect to extend all of the dates for the Critical Milestones not yet achieved by up to four six-month periods from the applicable dates set forth in Section 3.1(a) by posting additional Development Period Security in an amount equal to $[_______] (which is $5,000  per MWh per hour of Contract Maximum Amount) for each such six-month period.  Any such election shall be made in a written notice delivered to Buyer on or prior to the first date for a Critical Milestone that has not yet been achieved (as such date may have previously been extended).

To the extent a Force Majeure event pursuant to Section 10.1 has occurred that prevents Seller from achieving the Critical Milestone date for acquisition of real property rights and interconnection (Section 3.1(a)(iv)) or the Commercial Operation Date (Section 3.1(a)(viii)) by the applicable Milestone date, the Critical Milestone Date(s) impacted by such Force Majeure event shall be extended for the duration of the Force Majeure event, but under no circumstances shall extensions of those Critical Milestone dates due to Force Majeure events exceed twenty-four (24) months beyond the applicable Milestone date, and further provided, that Seller shall not have the right to declare a Force Majeure event related to the Permits Critical Milestones (Section 3.1(a)(iii) and (vii)) or the Financing Critical Milestone (Section 3.1(a)(v)).

The Parties agree that time is of the essence with respect to the Critical Milestones and is part of the consideration to Buyer in entering into this Agreement.

Notwithstanding the other provisions of this Agreement, or the rights of Seller under Sections 3.1(c), 3.1(d) and 10.1, in no event shall the Guaranteed Commercial Operation Date be extended beyond [_________].

Delay Damages.

If the Commercial Operation Date is not achieved by the Guaranteed Commercial Operation Date  (as extended pursuant to Sections 3.1(c) and 10.1), Seller shall pay to Buyer damages for each day from and after such date in an amount equal to $[_______] (which is $100.00 per MWh per hour of Contract Maximum Amount), commencing on the Guaranteed Commercial Operation Date (as extended pursuant to Sections 3.1(c) and 10.1) and ending on the earlier of (i) the Commercial Operation Date, (ii) the date that Buyer exercises its right to terminate this Agreement under Section 9.3, or (iii) the date that is twelve (12) months after the Guaranteed Commercial Operation Date (“Delay Damages”).  Delay Damages shall be due under this Section 3.2(a) without regard to whether Buyer exercises its right to terminate this Agreement pursuant to Section 9.3; provided, however, that if Buyer exercises its right to terminate this Agreement under Section 9.3, Delay Damages shall be due and owing to the extent that such Delay Damages were due and owing at the date of such termination

- Notwithstanding anything in this Section 3.2(a) or Section 9.2(e) to the contrary, the Parties agree that, if the Commercial Operation Date is not achieved by the Guaranteed Commercial Operation Date and, at any time prior to the date on which Buyer exercises its right to terminate this Agreement under Section 9.3, Seller (x) provides an Independent Engineer’s certification, in form and substance reasonably acceptable to Buyer and with reasonable supporting detail and information, stating that the Commercial Operation Date is reasonably likely to occur on or prior to the date that is twelve (12) months after the Guaranteed Commercial Operation Date (as such date may be extended), (y) has exercised its rights to extend the Critical Milestone dates the maximum number of times allowed pursuant to Section 3.1(c), and (z) posts additional Development Period Security with a Value of [$___________] (which is equal to three hundred sixty five (365) days of Delay Damages), then Buyer shall not have any right to terminate this Agreement because of an Event of Default under Section 9.2(e) until the date that is twelve (12) months after the Guaranteed Commercial Operation Date (provided that Seller is paying Delay Damages in accordance with the provision of this Section 3.2(a)).

Each Party agrees and acknowledges that (i) the damages that Buyer would incur due to Seller’s delay in achieving the Commercial Operation Date by the Guaranteed Commercial Operation Date would be difficult or impossible to predict with certainty, and (ii) it is impractical and difficult to assess actual damages in the circumstances stated, and therefore the Delay Damages as agreed to by the Parties and set forth herein are a fair and reasonable calculation of such damages.  Notwithstanding the foregoing, this Article shall not limit the amount of damages payable to Buyer if this Agreement is terminated as a result of Seller’s failure to achieve the Commercial Operation Date.  Any such termination damages shall be determined in accordance with Article 9.

By the tenth (10th) day following the end of the calendar month in which Delay Damages first become due and continuing by the tenth (10th) day of each calendar month during the period in which Delay Damages accrue (and the following months if applicable), Buyer shall deliver to Seller an invoice showing Buyer’s computation of such damages and any amount due Buyer in respect thereof for the preceding calendar month.  No later than ten (10) days after receiving such an invoice, Seller shall pay to Buyer, by wire transfer of immediately available funds to an account specified in writing by Buyer or by any other means agreed to by the Parties in writing from time to time, the amount set forth as due in such invoice.  If Seller fails to pay such amounts when due, Buyer may draw upon the Development Period Security for payment of such Delay Damages, and Buyer may exercise any other remedies available for Seller’s default hereunder.

Construction and Changes in Capacity.

Construction of Facility.  Seller shall construct the Facility as described in Exhibit A, in accordance with Good Utility Practice, the manufacturer’s guidelines for all material components of the Facility and all requirements of the ISO-NE Rules and ISO-NE Practices for the delivery of the Products to Buyer.  Seller shall bear all costs related thereto.  Seller may contract with other Persons to provide construction functions, so long as Seller maintains overall control over the construction of the Facility through the Term.

Capacity Deficiency.  To the extent that Seller has constructed the Facility in accordance with Section 3.3(a), and met all other requirements for the Commercial Operation Date under Section 3.4(b) of this Agreement, including, without limitation, the requirement that the Actual Facility Size as of the Commercial Operation Date is at least ninety percent (90%) of the proposed nameplate capacity of the Facility as set forth in Exhibit A, but a Capacity Deficiency exists on the Commercial Operation Date as permitted by Section 3.4(b), then (i) on the Commercial Operation Date, the Contract Maximum Amount shall be automatically and temporarily reduced commensurate with the Capacity Deficiency, which reduced Contract Maximum Amount shall be stated in a notice from Buyer to Seller, which notice shall be binding absent manifest error, and (ii) Seller shall have a period of six (6) months following the Commercial Operation Date to attempt to increase the Actual Facility Size to an amount not to exceed the proposed nameplate capacity of the Facility as set forth in Exhibit A (the “Additional Construction Period”).  On the earlier of (A) the date that (I)(x) the portions of the Facility constructed during the Additional Construction Period have been completed in all material respects (excepting punchlist items that do not affect the ability of the Facility, Network Upgrades and Related Transmission Facilities to operate as intended hereunder) in accordance with this Agreement and are capable of regular commercial operation in accordance with Good Utility Practice and the manufacturer’s guidelines for all material components of the Facility, (y) all requirements of the ISO-NE Rules and ISO-NE Practices for the delivery of the Products to Buyer have been satisfied and (z) all performance testing for such portions of the Facility has been successfully completed (provided that all of the conditions precedent set forth in Section 3.4(b) remain satisfied after giving effect to the portions of the Facility constructed during the Additional Construction Period); and (II) Seller has delivered to Buyer the Additional Construction Certificates and certificates of insurance evidencing the coverages required under Section 3.5(i) for the Facility after giving effect to the portions of the Facility constructed during the Additional Construction Period and (B) the last day of the Additional Construction Period, the Contract Maximum Amount and the Operating Period Security shall be automatically and permanently adjusted commensurate with the Actual Facility Size as certified by an Independent Engineer, as provided in Section 3.4(b)(xv)(A) or in any Additional Construction IE Certificate delivered pursuant to this Section 3.3(b).  Notwithstanding anything to the contrary in this Section 3.3(b), (x) the Services Term shall commence on the Commercial Operation Date, and (y) the same Services Term shall apply to the capacity of the Facility constructed as of the Commercial Operation Date and any remaining capacity of the Facility constructed during the Additional Construction Period, and (z) the Services Term shall not be extended for any remaining capacity of the Facility constructed during the Additional Construction Period.

Increase in Facility Size.  To the extent that Seller has constructed the Facility in accordance with Section 3.3(a), and met all other requirements under Section 3.4(b) of this Agreement, if the Independent Engineer’s certification provides that the Actual Facility Size exceeds the Proposed Facility Size as provided in Exhibit A, the Buyer’s Percentage Entitlement will be recalculated and replaced by the percentage derived by dividing Contract Maximum Amount by the Actual Facility Size. The Actual Facility Size shall not in any event exceed [___] MW.

Progress Reports.  Within ten (10) days of the end of each calendar quarter that ends after the Effective Date and continuing until the Commercial Operation Date, Seller shall provide Buyer with a progress report regarding the development, construction and start-up of the Facility and Critical Milestones not yet achieved, including projected time to completion of the Facility, in accordance with the form attached hereto as Exhibit C, and shall provide supporting documents and detail supporting any claim that a Critical Milestone has been achieved and other documents and details upon Buyer’s request.  Seller shall permit Buyer and its advisors and consultants to review and discuss with Seller and its advisors and consultants such progress reports during business hours and upon reasonable notice to Seller. The Parties intend that, within five (5) to ten (10) days following the issuance of each progress report, Buyer and Seller shall have a conference to discuss the status of the project including the matters addressed in the progress report.

Site Access.  Buyer and its representatives shall have the right but not the obligation, during business hours and upon reasonable notice to Seller, to inspect the Facility site and view the construction of the Facility, subject to Seller’s reasonable site access rules.

Exhibit Updates.  Within thirty (30) days after the Commercial Operation Date and after the delivery of each Additional Construction Certificate, as applicable, Seller shall provide Buyer with an updated version of Exhibit A and Exhibit E solely to reflect the Actual Facility Size, the serial number of each turbine included in the Facility, and the Related Transmission Facilities, each as built and configured as of such date.  Any changes to any Exhibit other than as provided in this Section 3.3(f) will require Buyer’s consent.

Commercial Operation.

Seller’s obligation to Deliver the Products and Buyer’s obligation to pay Seller for such Products commences on the Commercial Operation Date; provided, that Energy and RECs generated by the Facility prior to the Commercial Operation Date (the “Test Period”) shall not be deemed Products.

The Commercial Operation Date shall occur on the date on which Seller provides Buyer with a certificate of Seller’s chief executive officer, chief operating officer, chief financial officer or another officer of a similar level in Seller’s organization notifying Buyer that (A) the Facility as described in Exhibit A is completed (subject, if applicable, to a Capacity Deficiency) so long as the Actual Facility Size on the Commercial Operation Date is at least ninety percent (90%) of the proposed nameplate capacity of the Facility as set forth in Exhibit A and capable of regular commercial operation in accordance with Good Utility Practice, the manufacturer’s guidelines for all material components of the Facility, (B) all requirements of the ISO-NE Rules and ISO-NE Practices for the delivery of the Products to Buyer have been satisfied, (C) all performance testing for the Facility has been successfully completed, and (D) Seller has also satisfied the following conditions precedent as of such date:

completion of all transmission and interconnection facilities and any and all Network Upgrades, including those included in Exhibit F and final acceptance and authorization to interconnect the Facility from ISO-NE or the Interconnecting Utility in accordance with the fully executed Interconnection Agreement and as required to interconnect the Facility at the Interconnection Point at a level that is capable of satisfying the Network Capability Interconnection Standard and that is equivalent to  the Capacity Capability Interconnection Standard both as defined under the ISO-NE Rules;

all Related Transmission Facilities as set forth in Exhibit E are complete and in-service;

Seller has obtained and demonstrated possession of all Permits required for the lawful construction and operation of the Facility, for the interconnection of the Facility to the Interconnecting Utility (including any Network Upgrades) and for Seller to perform its obligations under this Agreement, including but not limited to Permits related to environmental matters, all as set forth on Exhibit B;

Seller has obtained qualification by the DOER qualifying the Facility as a RPS Class I Renewable Generation Unit and as a Clean Peak Resource  (subject to Section 4.1(b));

Seller has satisfied all requirements in order to provide for unit-specific accounting of Environmental Attributes, enabling the Massachusetts Department of Environmental Protection to accurately account for the Energy in the state greenhouse gas emissions inventory, created under chapter 298 of the Acts of 2008;

all Related Transmission Approvals have been received;

Seller has acquired all real property rights needed to construct and operate the Facility, to interconnect the Facility to the Interconnecting Utility, to construct the Network Upgrades (to the extent that it is Seller’s responsibility to do so) and to perform Seller’s obligations under this Agreement;

Seller (or the party with whom Seller contracts pursuant to Section 3.5(e)) has established all ISO-NE-related accounts and entered into all ISO-NE-related agreements required for the performance of Seller’s obligations in connection with the Facility and this Agreement, which agreements shall be in full force and effect;

Seller has registered the Facility in the GIS;

Seller has provided to Buyer I.3.9 Confirmation from ISO-NE regarding approval of generation entry, has submitted the Asset Registration Form (as defined in ISO-NE Practices) for the Facility to ISO-NE and has taken such other actions as are necessary to effect the Delivery of the Energy to Buyer in the ISO Settlement Market System;

Seller has successfully completed all pre-operational testing and commissioning in accordance with manufacturer guidelines;

Seller has satisfied all Critical Milestones that precede the Commercial Operation Date in Section 3.1;

no Default or Event of Default by Seller shall have occurred and remain uncured;

the Facility is owned or leased by, and under the care, custody and control of, Seller.

Seller has delivered to Buyer:

an Independent Engineer’s certification stating (i) that the Facility has been completed in all material respects (excepting punchlist items that do not materially and adversely affect the ability of the Facility and the Network Upgrades to operate as intended hereunder) in accordance with this Agreement, and (ii) the Actual Facility Size; and

certificates of insurance evidencing the coverages required under Section 3.5(i); and

Seller has demonstrated that it can reliably transmit real time data and measurements to ISO-NE.

Operation of the Facility.

Compliance With Utility Requirements.  Seller shall comply with, and shall cause the Facility and Related Transmission Facilities to comply with Good Utility Practice and all applicable rules, procedures, operating policies, criteria, guidelines and requirements imposed by ISO-NE, any Transmission Provider, any Interconnecting Utility, NERC and/or any regional reliability entity, including, in each case, all practices, requirements, rules, procedures and standards related to Seller’s construction, ownership, operation and maintenance of the Facility and Related Transmission Facilities and its performance of its obligations under this Agreement (including obligations related to the generation, Scheduling, interconnection, and transmission of Energy, and the transfer of RECs), whether such requirements were imposed prior to, on or after the Effective Date.  Seller shall be solely responsible for registering as the “Generator Owner and Generator Operator” of the Facility with NERC and any applicable regional reliability entities, as applicable.

Permits.  Seller shall maintain or cause to be maintained in full force and effect all Permits necessary for it to perform its obligations under this Agreement, including all Permits necessary to construct, operate and maintain the Facility and all Related Transmission Approvals.

Maintenance and Operation of Facility.  Seller shall, at all times during the Term, construct, maintain and operate the Facility and Related Transmission Facilities in accordance with Good Utility Practice and in accordance with Exhibit A to this Agreement.  Seller shall bear all costs related thereto.  Seller may contract with other Persons to provide construction, operation and maintenance functions, so long as Seller maintains overall control over the construction, operation and maintenance of the Facility throughout the Term.

Interconnection Agreement.  Seller shall comply with the terms and conditions of the Interconnection Agreement and shall be responsible for obtaining interconnection of the Facility at the Interconnection Point at a level that is capable of satisfying both the Network Capability Interconnection Standard and the equivalent of the Capacity Capability Interconnection Standard under the ISO-NE Rules.

ISO-NE Status.  Seller shall, at all times during the Services Term, either:  (i) be an ISO-NE “Market Participant” pursuant to the ISO-NE Rules; or (ii) have entered into an agreement with a Market Participant that shall perform all of Seller’s ISO-NE-related obligations in connection with the Facility and this Agreement.

Forecasts.  Commencing at least thirty (30) days prior to the anticipated Commercial Operation Date and continuing throughout the Term, Seller shall update and deliver to Buyer on an annual basis and in a form reasonably acceptable to Buyer, twelve (12) month rolling forecasts of hourly Energy production by the Facility (including a forecast of the Clean Peak Energy Certificates to be produced by the Facility during the twelve (12) month period covered by such forecast), which forecasts shall be prepared in good faith and in accordance with Good Utility Practice based on historical performance, maintenance schedules, Seller’s generation projections and other relevant data and considerations.  Any notable changes from prior forecasts or historical energy delivery shall be noted and an explanation provided.  The provisions of this section are in addition to Seller’s requirements under ISO-NE Rules and ISO-NE Practices, including ISO-NE Operating Procedure No. 5.

RPS Class I Renewable Generation Unit, etc.  Subject to Section 4.1(b), Seller shall be solely responsible at Seller’s cost for qualifying the Facility as a RPS Class I Renewable Generation Unit and for qualifying the Facility for the CES and the Clean Peak Standard, for satisfying all requirements in order to provide for unit-specific accounting of Environmental Attributes, enabling the Massachusetts Department of Environmental Protection to accurately account for the Energy in the state greenhouse gas emissions inventory, created under chapter 298 of the Acts of 2008, for arranging for providing meter data for the Facility to the Clean Peak Standard program administrator designated by DOER from time to time, and for maintaining such qualifications throughout the Services Term.  Subject to Section 4.1(b), Seller shall take all actions necessary to register for and maintain participation in the GIS to register, monitor, track, and transfer RECs eligible to satisfy both the RPS and the Clean Peak Standard.  Seller shall provide such additional information as Buyer may reasonably request relating to such qualification and participation and the registration, monitoring, tracking and transfer of RECs.

Compliance Reporting.  Within thirty (30) days following the end of each calendar quarter, Seller shall provide Buyer information pertaining to emissions, fuel types, labor information, generation periods and any other information to the extent required by Buyer to comply with the disclosure requirements contained under applicable Law and any other such disclosure regulations which may be imposed upon Buyer during the Term, which information requirements will be provided to Seller by Buyer at least fifteen (15) days before the beginning of the calendar quarter for which the information is required.  To the extent Buyer is subject to any other certification or compliance reporting requirement with respect to the Products produced by Seller and delivered to Buyer hereunder, Seller shall provide any information in its possession (or, if not in Seller’s possession, available to it and not reasonably available to Buyer) requested by Buyer to permit Buyer to comply with any such reporting requirement.

Insurance.  Throughout the Term, and without limiting any liabilities or any other obligations of Seller hereunder, Seller shall secure and continuously carry with an insurance company or companies rated not lower than “A-” by the A.M. Best Company (or any successor thereto) the insurance coverage and with the deductibles that are customary for a generating facility of the type and size of the Facility and as otherwise legally required.  Upon the execution of this Agreement, and at each subsequent policy renewal date thereafter, Seller shall provide Buyer with a certificate of insurance which (i) shall include Buyer as an additional insured on each policy, (ii) shall not include the legend “certificate is not evidence of coverage” or any statement with similar effect, (iii) shall evidence a firm obligation of the insurer to provide Buyer with thirty (30) days prior written notice of coverage modifications that may adversely affect Buyer, and (iv) shall be endorsed by a Person who has authority to bind the insurer.  If any coverage is written on a “claims-made” basis, the certification accompanying the policy shall conspicuously state that the policy is “claims made.”

Contacts.  Each Party shall identify a principal contact or contacts, which contact(s) shall have adequate authority and expertise to make day-to-day decisions with respect to the administration of this Agreement.

Compliance with Law.  Without limiting the generality of any other provision of this Agreement, Seller shall be responsible for complying with all applicable requirements of Law, including all applicable rules, procedures, operating policies, criteria, guidelines and requirements imposed by FERC and any other Governmental Entity, whether imposed pursuant to existing Law or procedures or pursuant to changes enacted or implemented during the Term, including all risks of operational and environmental matters relating to the Facility or the Facility site.  Seller shall indemnify Buyer against any and all claims arising out of or related to such environmental matters and against any costs imposed on Buyer as a result of Seller’s violation of any applicable Law, or ISO-NE or NERC requirements.  For the avoidance of doubt, Seller shall be responsible for procuring, at its expense, all Permits and governmental approvals required for the construction and operation of the Facility in compliance with applicable requirements of Law.

    - FERC Status.  Seller shall be responsible for ensuring that it is in compliance with all FERC directives and requirements necessary for Seller to fulfill its obligations under this Agreement.  As part of Seller’s satisfaction of this responsibility, it shall maintain the Facility’s status as an EWG at all times on and after the Commercial Operation Date and shall obtain and maintain any requisite authority to sell the output of the Facility at market-based rates, including market-based rate authority to the extent applicable.  Notwithstanding, a change in Law occurring subsequent to the Effective Date, Seller shall not (i) seek to qualify the Facility as one or more QFs, or (ii) for so long as this Agreement is in effect, assert any rights Seller may have to require Buyer to purchase or transmit electric power or to pay a specified price for electric power by virtue of a QF status.

    - Maintenance.  No later than (a) the Commercial Operation Date and (b) two months prior to the end of each calendar year thereafter during the Term, Seller shall submit to Buyer a schedule of planned maintenance for the following calendar year for the Facility.  Throughout the Term, Seller shall coordinate all planned maintenance with ISO-NE, consistent with ISO-NE Rules, and shall promptly provide applicable information concerning scheduled outages, as determined by ISO-NE, to Buyer.  To maximize the value of the Products, to the extent possible and consistent with ISO-NE Rules, Seller (i) shall not schedule maintenance of the Facility during the months of December, January and February, (ii) shall not schedule maintenance requiring more than twenty percent (20%) of the Facility to be offline at any single time during the months of June through September, and (iii) shall operate the Facility so as to maximize energy production during the hours of anticipated peak load and Energy prices in New England; provided, however, that planned maintenance may be scheduled during all such periods to the extent the failure to perform such planned maintenance is contrary to operation of the Facility in accordance with Good Utility Practice.

Interconnection and Delivery Services.

Seller shall be responsible for all costs associated with Network Upgrades, including, but not limited to, interconnection of the Facility at the Interconnection Point at a level that is capable of satisfying both the Network Capability Interconnection Standard and the equivalent of the Capacity Capability Interconnection Standard under the ISO-NE Rules  (including the construction of those facilities described in Exhibit F), consistent with all standards and requirements set forth by the FERC, ISO-NE, any other applicable Governmental Entity and the Interconnecting Utility.  Seller shall be responsible for procuring delivery service to the Delivery Point and all costs associated with it.

Seller shall defend, indemnify and hold Buyer harmless against any and all liabilities, fees, costs and expenses, including but not limited to reasonable attorneys’ fees arising due to Seller’s performance or failure to perform under the Interconnection Agreement or any agreement for delivery service associated with Seller’s performance of its obligations under this Agreement.

  - Forward Capacity Market Participation.  Seller shall participate in the ISO-NE’s Forward Capacity Auction Qualification (“FCAQ”) process for, and take all other necessary and appropriate actions to qualify for, the Forward Capacity Auction (“FCA”) for the first full Capacity Commitment Period during the Services Term with a summer Seasonal Claimed Capability and a winter Seasonal Claimed Capability in each case not less than the respective maximum Seasonal Claimed Capabilities as determined by ISO-NE for Seller’s project as described in the Bid, including qualifying the Seasonal Claimed Capabilities described in the Bid for Capacity Capability Interconnection Standard-equivalent interconnection. Notwithstanding the above, actual Seller participation in any FCA or obtaining a Capacity Supply Obligation shall not be required, but may be pursued at the option of Seller.  Seller will provide Buyer with copies of all technical reports and studies provided to and/or by ISO-NE as part of the FCAQ process for the Facility, as described in this Section 3.7, at the same time when those materials are provided to and/or by ISO-NE.  Seller shall use commercially reasonable efforts, consistent with Good Utility Practice, to maximize the summer and winter Seasonal Claimed Capabilities for the Facility consistent with the technical reports and studies provided to and/or by ISO-NE and with the Bid.  Seller will provide Buyer with written notice of the summer and winter Seasonal Claimed Capabilities for the Facility and the Network Upgrades required to satisfy both the Network Capability Interconnection Standard and the equivalent of the Capacity Capability Interconnection Standard at the Interconnection Point at those Seasonal Claimed Capabilities within fifteen (15) days after the determination thereof by ISO-NE.

DELIVERY OF PRODUCTS

Obligation to Sell and Purchase Products.

Beginning on the Commercial Operation Date, Seller shall sell and Deliver, and Buyer shall purchase and receive all right, title and interest in and to, Buyer’s Percentage Entitlement of the Products in accordance with the terms and conditions of this Agreement.  The obligations for Seller to sell and Deliver the Products and for Buyer to purchase and receive the same hereunder are Unit Contingent and shall be subject to the operation of the Facility.  Seller agrees that Seller will not curtail or otherwise reduce deliveries of the Products in order to sell such Products to other purchasers.  To maximize the value of the Products and without limiting the application of Section 4.7(g), to the extent consistent with ISO-NE Rules and Good Utility Practice, Seller shall use commercially reasonable efforts to maximize the production and Delivery of Energy during the time periods of anticipated peak load and peak Energy.

In the event that, solely as a result of a change in Law occurring subsequent to the Effective Date, the Products provided by Seller to Buyer from the Facility under this Agreement do not meet the requirements of the RPS, the CES or the Clean Peak Standard, then Seller will continue to sell and Deliver, and Buyer will continue to purchase, Energy and RECs under this Agreement notwithstanding such change in Law, provided that Seller shall use commercially reasonable efforts consistent with Good Utility Practice to cause the Products provided by Seller to Buyer from the Facility under this Agreement to qualify and meet the requirements of the RPS, the CES and the Clean Peak Standard.  To the extent Seller has failed to use commercially reasonable efforts consistent with Good Utility Practice to cause the Products provided by Seller to Buyer under this Agreement to qualify and meet the requirements of the RPS, the CES and the Clean Peak Standard as provided above, Buyer shall be entitled to continue to purchase and receive all right, title and interest in and to Buyer’s Percentage Entitlement of the Products at the Energy-only price specified in Exhibit D. The foregoing shall not be construed to limit any of Buyer’s rights under Sections 9.2(j), (k) or (l) and Section 9.3 of this Agreement.

Seller shall Deliver Buyer’s Percentage Entitlement of the Products produced by or associated with the Facility, up to and including the Contract Maximum Amount, exclusively to Buyer, and Seller shall not sell, divert, grant, transfer or assign such Products or any right, claim, certificate or other attribute associated with such Products to any Person other than Buyer during the Term.  Seller shall not enter into any agreement or arrangement under which such Products can be claimed by any Person other than Buyer.  Buyer shall have the exclusive right to resell or convey the Products in its sole discretion.  Buyer shall not purchase Energy or RECs in excess of the Contract Maximum Amount under this Agreement.

To the extent that Seller receives any payment or other consideration for any Environmental Attributes to be purchased under this Agreement directly from any other Person, Seller shall hold such payment or other consideration in trust for the benefit of Buyer and shall promptly remit such payment or other consideration to Buyer in the form so received, or if not transferrable in such form, in the cash equivalent of such form.

Scheduling and Delivery.

During the Services Term and in accordance with Section 4.1, Seller shall Schedule and Deliver Energy hereunder with ISO-NE in accordance with this Agreement and all ISO-NE Practices and ISO-NE Rules to Buyer through Internal Bilateral Transactions executed through ISO-NE and settled at the Delivery Point, in accordance with all ISO-NE Practices and ISO-NE Rules. Any such Internal Bilateral Transactions will specify the Buyer’s Percentage Entitlement to the actual metered hourly delivery of Energy and will be entered into daily, with any necessary adjustments being made pursuant to ISO-NE settlement protocols, and Seller will not receive any payment associated with a Marginal Loss Revenue Fund allocation in connection with any such Internal Bilateral Transactions.  Any such Internal Bilateral Transactions will be entered (x) in the Day Ahead Energy Market if the Energy is offered by Seller and settled in the Day Ahead Energy Market, (y) in the Real Time Energy Market if the Energy is offered by Seller and settled in the Real Time Energy Market, and/or (z) as reasonably agreed to from time to time by Buyer and Seller, in another ISO-NE energy market to the extent that such other market provides Buyer with additional value for the Energy being purchased hereunder, in each case consistent with ISO-NE Rules and ISO-NE Practices at the time, and Buyer shall have no obligation to pay for any Energy not transferred to Buyer in the Day Ahead Energy Market or Real Time Energy Market and/or such other ISO-NE energy market as reasonably agreed to from time to time by Buyer and Seller or for which Buyer is not credited in the ISO-NE Settlement Market System (including, without limitation, as a result of an outage on any electric transmission system).  In the event Seller does not have actual metered generation by the Internal Bilateral Transaction initial settlement deadlines, Seller shall Schedule and Deliver Energy through Internal Bilateral Transactions executed through the ISO-NE Data Reconciliation Process.  Under no circumstances shall Seller enter estimated generation values into an Internal Bilateral Transaction.  Notwithstanding any other provision of this Agreement, if during the Services Term the LMP in the Real Time Energy Market or the Day Ahead Energy Market, as applicable, at the Delivery Point is negative, then Seller may deliver to Buyer a written notice stating that such condition has occurred and the period during which such condition has occurred, and in such event Seller shall be under no obligation to schedule or Deliver Products at the Delivery Point during such negative LMP period.

The Parties agree to use commercially reasonable efforts to comply with all applicable ISO-NE Rules and ISO-NE Practices in connection with the Scheduling and Delivery of Energy hereunder. Without limiting the foregoing, Seller shall submit an Internal Bilateral Transaction for the Energy being Delivered by the applicable scheduling deadline and Buyer shall confirm the Internal Bilateral Transaction submitted by Seller by the applicable scheduling deadline. Penalties or similar charges assessed by a Transmission Provider and caused by Seller’s noncompliance with the Scheduling obligations set forth in this Section 4.2 shall be the responsibility of Seller.

Without limiting the generality of this Section 4.2, Seller or the party with whom Seller contracts pursuant to Section 3.5(e) shall at all times during the Services Term be designated with ISO-NE as the “Lead Market Participant” (or any successor designation) for the Facility and shall be solely responsible for any obligations and liabilities imposed by ISO-NE or under the ISO-NE Rules and ISO-NE Practices with respect to the Facility, including all charges, penalties, financial assurance obligations, losses, transmission charges, ancillary service charges, line losses, congestion charges and other ISO-NE or applicable system costs or charges associated with transmission and delivery.  To the extent Buyer incurs such costs, charges, penalties or losses which are the responsibility of Seller, (including amounts not credited to Buyer as described in Section 4.2(a)), Seller shall reimburse Buyer for the same.

[FOR ENERGY STORAGE PROPOSALS:  The EDCs will draft into the PPA with the winning bidder(s) the terms of any energy storage proposal included in the winning bid(s).  An energy storage proposal must be specific and must include at a minimum the following components:  times or criteria for charging and discharging, metering requirements, criteria for commercial operation, plans for maintenance of the storage facility, plans to maximize the value for purposes of the Clean Peak Standard, and a calculation of liquidated damages that holds Buyer harmless for all losses and costs for Seller’s failure to comply with those terms.]

Failure of Seller to Deliver Products.  In the event that Seller fails to satisfy any of its obligations to Deliver any of the Products or any portion of the Products hereunder in accordance with Section 4.1, Section 4.2 and Section 4.7, and such failure is not excused under the express terms of this Agreement (a “Delivery Failure”), (and without limiting Buyer’s rights under Section 9.2(h) and Section 9.3), Seller shall (i) consistent with ISO-NE Rules and ISO-NE Practices process a corrective (or resettlement) Internal Bilateral Transaction for the Energy through ISO-NE and transfer the RECs through the GIS solely to account for Energy that was generated by the Facility and transmitted to the Delivery Point during the applicable time interval but not credited to the Buyer’s ISO-NE account, or (ii) pay Buyer an amount for such Delivery Failure (measured in MWh and/or RECs) equal to the Cover Damages for such Delivery Failure.  Such payment shall be due no later than the date for Buyer’s payment for the applicable month as set forth in Section 5.2 hereof.  Each Party agrees and acknowledges that (i) the damages that Buyer would incur due to a Delivery Failure would be difficult or impossible to predict with certainty, and (ii) it is impractical and difficult to assess actual damages in the circumstances stated, and therefore the Cover Damages as agreed to by the Parties and set forth herein is a fair and reasonable calculation of such damages.

Failure by Buyer to Accept Delivery of Products.  If Buyer fails to accept all or part of any of the Products to be purchased by Buyer hereunder, and such failure to accept (a) is not the result of Reliability Curtailment or (b) is not otherwise excused under the terms of this Agreement (a “Rejected Purchase”), then Buyer shall pay Seller, on the date payment would otherwise be due in respect of the month in which the failure occurred, an amount for such Rejected Purchase equal to the Resale Damages.  Each Party agrees and acknowledges that (i) the damages that Seller would incur due to a Rejected Purchase would be difficult or impossible to predict with certainty, and (ii) it is impractical and difficult to assess actual damages in the circumstances stated, and therefore the Resale Damages as agreed to by the Parties and set forth herein is a fair and reasonable calculation of such damages.

Delivery Point.

All Energy shall be Delivered hereunder by Seller to Buyer at the Delivery Point.  Seller shall be responsible for the costs of delivering its Energy to the Delivery Point consistent with all standards and requirements set forth by the FERC, ISO-NE, and any other applicable Governmental Entity or applicable tariff.

Seller shall be responsible for all applicable charges associated with transmission and interconnection service and delivery charges, including all related ISO-NE administrative fees, uplift, socialized charges, all costs for Network Upgrades, all costs for Related Transmission Facilities, and all other charges in connection with the satisfaction of Seller’s obligations hereunder, including without limitation the Delivery of Energy to and at the Delivery Point.  Seller shall indemnify and hold harmless Buyer for any such charges, fees, costs or expenses imposed upon Buyer by operation of ISO-NE Rules or otherwise in connection with Seller’s performance of its obligations hereunder.

    - Buyer shall be responsible for all applicable charges associated with transmission and delivery of the Energy from and after the Delivery Point, provided that Buyer shall have no responsibility or liability for any Network Upgrade or the cost of constructing or upgrading any other transmission or distribution facilities.

Metering.

Metering.  All electric metering associated with the Facility, including the meter at the Delivery Point and any other real-time meters, billing meters and back-up meters (collectively, the “Meters”), shall be installed, operated, maintained and tested at Seller’s expense in accordance with Good Utility Practice and any applicable requirements and standards issued by NERC, the Interconnecting Utility, ISO-NE and DOER or its designated program administrator for the Clean Peak Standard (subject to Section 4.1(b)); provided that each Meter shall be tested at Seller’s expense once each Contract Year.  All Meters used to measure the Energy Delivered at the Delivery Point shall be sealed, and Seller shall break the seal only when such Meters are to be inspected and tested (or adjusted) in accordance with this Section 4.6.  Seller shall provide Buyer with a copy of all metering and calibration information and documents regarding the Meters promptly following receipt thereof by Seller.  All Meters and SCADA equipment associated with the Facility shall be installed, operated, maintained and tested at Seller’s expense in accordance with Good Utility Practice and the accuracy standards of the American National Standards Institute (ANSI) C12, with the accuracy class required by the ISO-NE Rules for revenue-quality meters. Seller shall provide Meter data to DOER or its designated program administrator in order for Buyer to receive RECs that satisfy the Clean Peak Standard.

Measurements.  Readings of the Meters at the Facility by the Interconnecting Utility (or an independent Person mutually acceptable to the Parties) shall be conclusive as to the amount of Energy generated by the Facility; provided however, that Seller, upon request of Buyer and at Buyer’s expense (if more frequently than annually as provided for in Section 4.6(a)), shall cause the Meters to be tested by the Interconnecting Utility in whose territory the Facility is located, and if any Meter is out of service or is determined to be registering inaccurately by more than two percent (2%), (i) the measurement of Energy produced by the Facility shall be adjusted as far back as can reasonably be ascertained, but in no event shall such period exceed six (6) months from the date that such inaccuracy was discovered, in accordance with the filed tariff of such Interconnecting Utility or the ISO-NE Tariff, whichever is applicable, and any adjustment shall be reflected in the next invoice provided by Seller to Buyer hereunder and (ii) Seller shall reimburse Buyer for the cost of such test of the Meters.  Meter readings shall be adjusted to take into account the losses to Deliver the Energy to the Delivery Point.  Seller shall make recorded meter data available monthly to Buyer at no cost.

Inspection, Testing and Calibration.  Buyer shall have the right to inspect and test (at its own expense) any of the Meters at the Facility at reasonable times and upon reasonable notice from Buyer to Seller.  Buyer shall have the right to have a representative present during any testing or calibration of the Meters at the Facility by Seller.  Seller shall provide Buyer with timely notice of any such testing or calibration.

Audit of Meters.  Buyer shall have access to the Meters and the right to audit all information and test data related to such Meters.

Notice of Malfunction.  Seller shall provide Buyer with prompt notice of any malfunction or other failure of the Meters or other telemetry equipment necessary to accurately report the quantity of Energy being produced by the Facility.  If any Meter is found to be inaccurate by more than two percent (2%), the meter readings shall be adjusted as far back as can reasonably be ascertained, but in no event shall such period exceed six (6) months from the date that such inaccuracy was discovered, and any adjustment shall be reflected in the next invoice provided by Seller to Buyer hereunder.

Telemetry.  The Meters shall be capable of sending meter telemetry data, and Seller shall provide Buyer with simultaneous access to such data at no additional cost to Buyer.  This provision is in addition to Seller’s requirements under ISO-NE Rules and Practices, including ISO-NE Operating Procedure No. 18.

RECs.

Seller shall transfer to Buyer all of the right, title and interest in and to Buyer’s Percentage Entitlement of the Environmental Attributes, including any and all RECs, generated by, or associated with, the Facility during the Services Term in accordance with the terms of this Section 4.7.

Except as provided in Section 4.1(b), all Energy and RECs provided by Seller to Buyer from the Facility under this Agreement shall meet the requirements for eligibility pursuant to the RPS, the CES and the Clean Peak Energy Standard.

At Seller’s sole cost, Seller shall also obtain and maintain throughout the Services Term qualification as a Class I generation resource under the renewable portfolio standard or similar law of each of Connecticut, Maine, Massachusetts, New Hampshire, New York and Rhode Island and any federal renewable energy standard, in each case to the extent the renewable energy technology used in the Facility is eligible under such renewable portfolio standard or similar law or program.  Seller shall use commercially reasonable efforts, consistent with Good Utility Practice, to maintain such qualifications at all times during the Services Term unless otherwise agreed by Buyer.  Seller shall also submit to Buyer or as directed by Buyer any information required by any state or federal agency with regard to administration of its rules regarding Environmental Attributes or its renewable energy standard, clean energy standard or renewable portfolio standard or Seller’s qualification under the foregoing.

Seller shall comply with all GIS Operating Rules, including without limitation such Rules relating to the creation, tracking, recording and transfer of all RECs to be purchased by Buyer under this Agreement.  In addition, at Buyer’s request, Seller shall register with and comply with the rules and requirements of any other tracking system or program that tracks, monetizes or otherwise creates or enhances value for Environmental Attributes, which compliance shall be at Seller’s sole cost if such registration and compliance is requested in connection with Section 4.7(c) above and shall be at Buyer’s sole cost in other instances.

Prior to the delivery of any Energy hereunder, either (i) Seller shall cause Buyer to be registered in the GIS as the initial owner of all Certificates to be Delivered hereunder to Buyer or (ii) Seller and Buyer shall effect an irrevocable Forward Certificate Transfer (as defined in the GIS Operating Rules) of the Certificates to be Delivered hereunder to Buyer in the GIS for the Services Term; provided, however, that no payment shall be due to Seller for any RECs until either (x) the Certificates are actually deposited in Buyer’s GIS account or a GIS account designated by Buyer to Seller in writing, or (y) (i) Buyer and Seller enter such an irrevocable Forward Certificate Transfer of the Certificates to be Delivered to Buyer in the GIS, which Forward Certificate Transfer shall be denoted in the GIS as not being capable of rescission by Seller, and (ii) the Energy with which such RECs are associated has been Delivered to Buyer.

The Parties intend for the transactions entered into hereunder to be physically settled, meaning that the RECs are intended to be Delivered in the GIS account of Buyer or its designee as set forth in this Section 4.7.

For the avoidance of doubt, the Parties intend that Seller shall Deliver to Buyer or otherwise cause Buyer to receive the maximum value of any Environmental Attributes.  Promptly following a request by Buyer, and at Seller’s sole cost, Seller shall execute, deliver, register, qualify, file, and take any other action that may be necessary or desirable for Seller to Deliver the Environmental Attributes to Buyer or to enable Buyer to receive and use the maximum value of the Environmental Attributes.

Test Period.  During the Test Period, Seller shall not sell and Deliver to Buyer, and Buyer shall not purchase and receive, any Energy or RECs produced by or associated with the Facility.  Any Energy or RECs produced by or associated with the Facility during the Test Period may be sold to a Person other than Buyer.

PRICE AND PAYMENTS FOR PRODUCTS

Price for Products.  All Products Delivered to Buyer in accordance with this Agreement shall be purchased by Buyer at the Price specified in Exhibit D; provided, however, that to the extent Seller has failed to use commercially reasonable efforts consistent with Good Utility Practice to cause the Products provided by Seller to Buyer under this Agreement to qualify and meet the requirements of the RPS, the CES and the Clean Peak Standard as applied to Buyer as provided in Section 4.1(b), Buyer shall purchase the Products at the Energy-only price specified in Exhibit D. Other than the (i) payment for the Products under this Section 5.1, (ii) payments related to Meter testing under Section 4.6(b), (iii) payments related to Meter malfunctions under Section 4.6(e), (iv) payment of any Resale Damages under Section 4.4, (v) payment of interest on late payments under Section 5.3, (vi) payments for reimbursement of Buyer’s Taxes under Section 5.4(a), (vii) return of any Credit Support under Section 6.2, and (viii) payment of any Termination Payment due from Buyer under Section 9.3, Buyer shall not be required to make any other payments to Seller under this Agreement, and Seller shall be solely responsible for all costs and losses incurred by it in connection with the performance of its obligations under this Agreement.  In the event that the LMP for the Energy at the Delivery Point is less than $0.00 per MWh in any hour, Seller shall credit to Buyer, on the appropriate monthly invoice, an amount equal to the product of (i) such Energy delivered in such hour and (ii) the absolute value of the hourly LMP at the Delivery Point.

Payment and Netting.

Billing Period.  The calendar month shall be the standard period for all charges and payments under this Agreement.  On or before the fifteenth (15th) day following the end of each month, Seller shall render to Buyer an invoice for the payment obligations incurred hereunder during the preceding month, based on the Energy Delivered in the preceding month, and any RECs deposited in Buyer’s GIS account or a GIS account designated by Buyer to Seller in writing in the preceding month.  Such invoice shall contain supporting detail for all charges reflected on the invoice, and Seller shall provide Buyer with additional supporting documentation and information as Buyer may request.

Timeliness of Payment.  All undisputed charges shall be due and payable in accordance with each Party’s invoice instructions on or before the later of (x) fifteen (15) days from receipt of the applicable invoice or (y) the last day of the calendar month in which the applicable invoice was received (or in either event the next Business Day if such day is not a Business Day).  Each Party shall make payments by electronic funds transfer, or by other mutually agreeable method(s), to the account designated by the other Party.  Any undisputed amounts not paid by the due date shall be deemed delinquent and shall accrue interest at the Late Payment Rate, such interest to be calculated from and including the due date to but excluding the date the delinquent amount is paid in full.

Disputes and Adjustments of Invoices.

All invoices rendered under this Agreement shall be subject to adjustment after the end of each month in order to true-up charges based on changes resulting from ISO-NE billing statements or revisions, if any, to previous ISO-NE billing statements.  If ISO-NE resettles any invoice which relates to the Products sold under this Agreement and (a) any charges thereunder are the responsibility of the other Party under this Agreement or (b) any credits issued thereunder would be due to the other Party under this Agreement, then the Party receiving the invoice from ISO-NE shall in the case of (a) above invoice the other Party or in the case of (b) above pay the amount due to the other Party.  Any invoices issued or amounts due pursuant to this Section shall be invoiced or paid as provided in this Section 5.2.

Within twelve (12) months of the issuance of an invoice Seller shall adjust any invoice for any arithmetic or computational error and shall provide documentation and information supporting such adjustment to Buyer.  Within twelve (12) months of the receipt of an invoice (or an adjusted invoice), Buyer may dispute any charges on that invoice.  In the event of such a dispute, Buyer shall give notice to Seller and shall state the basis for the dispute.  Payment of the disputed amount shall not be required until the dispute is resolved.  Upon resolution of the dispute, any required payment or refund shall be made within ten (10) days of such resolution along with interest accrued at the Late Payment Rate from and including the due date (or in the case of a refund, the payment date) but excluding the date paid.  Any claim for additional payment is waived unless Seller issues an adjusted invoice within twelve (12) months of issuance of the original invoice.  Any dispute of charges is waived unless Buyer provides notice of the dispute to Seller within twelve (12) months of receipt of the invoice (or adjusted invoice) including such charges.

Netting of Payments.  The Parties hereby agree that they may discharge mutual debts and payment obligations due and owing to each other under this Agreement on the same date through netting of such monetary obligations, in which case all amounts owed by each Party to the other Party for the purchase and sale of Products during the monthly billing period under this Agreement, including any related damages calculated pursuant to this Agreement, interest, and payments or credits, may be netted so that only the excess amount remaining due shall be paid by the Party who owes it.  If no mutual debts or payment obligations exist and only one Party owes a debt or obligation to the other during the monthly billing period, such Party shall pay such sum in full when due.  The Parties agree to provide each other with reasonable detail of such net payment or net payment request.

Interest on Late Payment or Refund.  A late payment charge shall accrue on any late payment or refund as specified above at the lesser of (a) the prime rate specified in the “Money & Investing” section of The Wall Street Journal (or, if such rate is not published therein, in a successor index mutually selected by the Parties) plus one percent (1%), and (b) the maximum rate permitted by applicable Law in transactions involving entities having the same characteristics as the Parties (the “Late Payment Rate”).

Taxes, Fees and Levies.

Seller shall be obligated to pay all present and future taxes, fees and levies, imposed on or associated with the Facility or Delivery or sale of the Products (“Seller’s Taxes”).  Buyer shall be obligated to pay all present and future taxes, fees and levies, imposed on or associated with such Products after Delivery of such Products to Buyer, or imposed on or associated with the purchase of such Products by Buyer (other than ad valorem, franchise or income taxes which are related to the sale of the Products and are, therefore, the responsibility of Seller) (“Buyer’s Taxes”).  In the event Seller shall be required by law or regulation to remit or pay any Buyer’s Taxes, Buyer shall reimburse Seller for such payment.  In the event Buyer shall be required by law or regulation to remit or pay any Seller’s Taxes, Seller shall reimburse Buyer for such payment, and Buyer may also elect to deduct any of the amount of any such Seller’s Taxes from the amount due to Seller under Section 5.2.  Buyer shall have the right to all credits, deductions and other benefits associated with taxes paid by Buyer or reimbursed to Seller by Buyer as described herein.  Nothing shall obligate or cause a Party to pay or be liable to pay any taxes, fees and levies for which it is exempt under law.

Seller shall bear all risks, financial and otherwise, throughout the Term, associated with Seller’s or the Facility’s eligibility to receive any federal or state tax credits, to qualify for accelerated depreciation for Seller’s accounting, reporting or tax purposes, or to receive any other favorable tax or accounting right or benefit, or any grant or subsidy from a Governmental Entity or other Person.  Seller’s obligations under this Agreement shall be effective regardless of whether the Facility is eligible for or receives, or the transactions contemplated under this Agreement are eligible for or receive, any federal or state tax credits, grants or other subsidies or any particular accounting, reporting or tax treatment.

SECURITY FOR PERFORMANCE

Seller’s Support.

Seller shall be required to post Credit Support in the amount of $[______________] [$40,000.00 per MWh per hour of Contract Maximum Amount ], as adjusted in accordance with Section 3.1(c), to secure Seller’s obligations in the period between the Effective Date and the Commercial Operation Date (“Development Period Security”).  Fifty percent (50%) of the Development Period Security shall be provided to Buyer on the Effective Date; and the remaining fifty percent (50%) of the Development Period Security shall be provided to Buyer within fifteen (15) Business Days after receipt of the Regulatory Approval.  If at any time, the amount of Development Period Security is reduced as a result of Buyer’s draw upon such Development Period Security to less than the amount of Development Period Security required to be provided by Seller, within five (5) Business Days of that draw Seller shall replenish such Development Period Security to the amount of Development Period Security required to be provided by Seller through the period ending fifteen (15) days after receipt of the Regulatory Approval.  Buyer shall return any undrawn amount of the Development Period Security to Seller within thirty (30) days after the later of (x) Buyer’s receipt of an undisputed notice from Seller that the Commercial Operation Date has occurred or (y) Buyer’s receipt of the full amount of the Operating Period Security (except to the extent that Development Period Security is converted into Operating Period Security as provided in Section 6.1(b)).

Beginning not later than ten (10) days following the Commercial Operation Date, Seller shall provide Buyer with Credit Support to secure Seller’s obligations under this Agreement after the Commercial Operation Date through and including the date that all of Seller’s obligations under this Agreement are satisfied (“Operating Period Security”).  The Operating Period Security shall be in the amount of $[_______] [$40,000.00 per MWh per hour of Contract Maximum Amount], as adjusted in accordance with Section 3.3(b).  If at any time on or after the Commercial Operation Date, the amount of Operating Period Security is reduced as a result of Buyer’s draw upon such Operating Period Security, within five (5) Business Days of that draw Seller shall replenish such Operating Period Security to the total amount required under this Section 6.1(b).

Return of Credit Support.  Any unused Credit Support provided under this Agreement shall be returned to Seller only after any such Credit Support has been used to satisfy any outstanding obligations of Seller in existence at the time of the expiration or termination of this Agreement.

Buyer’s Rights and Remedies.  If at any time an Event of Default with respect to Seller has occurred and is continuing, then, unless Seller has paid in full all of its obligations hereunder that are then due, without limiting any other rights and remedies Buyer may have under this Agreement or otherwise at law or in equity, Buyer may exercise one or more of the following rights and remedies:  (i) all rights and remedies available to a secured party under applicable Law with respect to Credit Support held by Buyer, and (ii) the right to liquidate any Credit Support held by Buyer and to apply the proceeds of such liquidation to any amounts payable to Buyer with respect to Seller’s obligations hereunder in such order as Buyer may elect.  For purposes of this Section 6.3, Buyer may draw on the undrawn portion of any letter of credit provided as Credit Support up to the amount of the Seller’s outstanding obligations hereunder.  Seller shall remain liable for amounts due and owed to Buyer that remain unpaid after the application of Credit Support pursuant to this Section 6.3.

REPRESENTATIONS, WARRANTIES, COVENANTS AND ACKNOWLEDGEMENTS

Representations and Warranties of Buyer.  Buyer hereby represents and warrants to Seller as follows:

Organization and Good Standing; Power and Authority.  Buyer is a corporation duly incorporated, validly existing and in good standing under the laws of the Commonwealth of Massachusetts.  Subject to the receipt of the Regulatory Approval, Buyer has all requisite power and authority to execute, deliver, and perform its obligations under this Agreement.

Due Authorization; No Conflicts.  The execution and delivery by Buyer of this Agreement, and the performance by Buyer of its obligations hereunder, have been duly authorized by all necessary actions on the part of Buyer and do not and, under existing facts and Law, shall not:  (i) contravene its certificate of incorporation or any other governing documents; (ii) conflict with, result in a breach of, or constitute a default under any note, bond, mortgage, indenture, deed of trust, license, contract or other agreement to which it is a party or by which any of its properties may be bound or affected; (iii) subject to receipt of the Regulatory Approval, violate any order, writ, injunction, decree, judgment, award, statute, law, rule, regulation or ordinance of any Governmental Entity or agency applicable to it or any of its properties; or (iv) result in the creation of any lien, charge or encumbrance upon any of its properties pursuant to any of the foregoing.

Binding Agreement.  This Agreement has been duly executed and delivered on behalf of Buyer and, assuming the due execution hereof and performance hereunder by Seller and receipt of the Regulatory Approval, constitutes a legal, valid and binding obligation of Buyer, enforceable against it in accordance with its terms, except as such enforceability may be limited by law or principles of equity.

No Proceedings.  As of the Effective Date, except to the extent relating to the Regulatory Approval, there are no actions, suits or other proceedings, at law or in equity, by or before any Governmental Entity or agency or any other body pending or, to the best of its knowledge, threatened against or affecting Buyer or any of its properties (including, without limitation, this Agreement) which relate in any manner to this Agreement or any transaction contemplated hereby, or which Buyer reasonably expects to lead to a material adverse effect on (i) the validity or enforceability of this Agreement or (ii) Buyer’s ability to perform its obligations under this Agreement.

Consents and Approvals.  Except to the extent associated with the Regulatory Approval, the execution, delivery and performance by Buyer of its obligations under this Agreement do not and, under existing facts and Law, shall not, require any Permit or any other action by, any Person which has not been duly obtained, made or taken or that shall be duly obtained, made or taken on or prior to the date required, and all such approvals, consents, permits, licenses, authorizations, filings, registrations and actions are in full force and effect, final and non-appealable as required under applicable Law.

Negotiations.  The terms and provisions of this Agreement are the result of arm’s length and good faith negotiations on the part of Buyer and equal bargaining power of the Parties.  No principle of law or equity regarding construing ambiguities in this Agreement against the drafting Party shall apply.

Bankruptcy.  There are no bankruptcy, insolvency, reorganization, receivership or other such proceedings pending against or being contemplated by Buyer, or, to Buyer’s knowledge, threatened against it.

No Default.  No Default or Event of Default has occurred and is continuing and no Default or Event of Default shall occur as a result of the performance by Buyer of its obligations under this Agreement.

Representations and Warranties of Seller.  Seller hereby represents and warrants to Buyer as of the Effective Date as follows:

Organization and Good Standing; Power and Authority.  Seller is a [______________], duly formed, validly existing and in good standing under the laws of [___________].  Subject to the receipt of the Permits listed in Exhibit B and any Related Transmission Approvals, Seller has all requisite power and authority to execute, deliver, and perform its obligations under this Agreement.

Authority.  Seller (i) has the power and authority to own and operate its businesses and properties, to own or lease the property it occupies and to conduct the business in which it is currently engaged; (ii) is duly qualified and in good standing under the laws of each jurisdiction where its ownership, lease or operation of property or the conduct of its business requires such qualification; and (iii) holds all rights and entitlements necessary to construct, own and operate the Facility and to deliver the Products to Buyer in accordance with this Agreement.

Due Authorization; No Conflicts.  The execution and delivery by Seller of this Agreement, and the performance by Seller of its obligations hereunder, have been duly authorized by all necessary actions on the part of Seller and do not and, under existing facts and Law, shall not:  (i) contravene any of its governing documents; (ii) conflict with, result in a breach of, or constitute a default under any note, bond, mortgage, indenture, deed of trust, license, contract or other agreement to which it is a party or by which any of its properties may be bound or affected; (iii) assuming receipt of the Permits listed on Exhibit B and any Related Transmission Approvals, violate any order, writ, injunction, decree, judgment, award, statute, law, rule, regulation or ordinance of any Governmental Entity or agency applicable to it or any of its properties; or (iv) result in the creation of any lien, charge or encumbrance upon any of its properties pursuant to any of the foregoing.  Seller is qualified to perform as a Market Participant under the ISO-NE Tariff, or is qualified to transact through another Market Participant under the ISO-NE Tariff.  Seller will not be disqualified from or be materially adversely affected in the performance of any of its obligations under this Agreement by reason of market power or affiliate transaction issues under federal or state regulatory requirements.

Binding Agreement.  This Agreement has been duly executed and delivered on behalf of Seller and, assuming the due execution hereof and performance hereunder by Buyer and receipt of the Permits listed on Exhibit B and any Related Transmission Approvals, constitutes a legal, valid and binding obligation of Seller, enforceable against it in accordance with its terms, except as such enforceability may be limited by law or principles of equity.

No Proceedings.  Except to the extent associated with the Permits listed on Exhibit B and any Related Transmission Approvals, there are no actions, suits or other proceedings, at law or in equity, by or before any Governmental Entity or agency or any other body pending or, to the best of its knowledge, threatened against or affecting Seller or any of its properties (including, without limitation, this Agreement) which relate in any manner to this Agreement or any transaction contemplated hereby, or which Seller reasonably expects to lead to a material adverse effect on (i) the validity or enforceability of this Agreement or (ii) Seller’s ability to perform its obligations under this Agreement.

Consents and Approvals.  Subject to the receipt of the Permits listed on Exhibit B on or prior to the date such Permits are required under applicable Law and subject to the receipt of the Related Transmission Approvals on or prior to the date such Related Transmission Approvals are required under applicable Law, the execution, delivery and performance by Seller of its obligations under this Agreement do not and, under existing facts and Law, shall not, require any Permit or any other action by, any Person which has not been duly obtained, made or taken, and all such approvals, consents, permits, licenses, authorizations, filings, registrations and actions are in full force and effect, final and non-appealable.  To Seller’s knowledge, Seller shall be able to receive the Permits listed in Exhibit B and the Related Transmission Approvals in due course and as required under applicable Law to the extent that those Permits or Related Transmission Approvals have not previously been received.

RPS Class I Renewable Generation Unit.  The Facility shall be (i) a RPS Class I Renewable Generation Unit, qualified by the DOER as eligible to participate in the RPS program, under Section 11F of Chapter 25A (subject to Section 4.1(b) in the event of a change in Law affecting such qualification as a RPS Class I Renewable Generation Unit), (ii) a Clean Peak Resource eligible under the Clean Peak Standard (subject to Sections 4.1(b) in the event of a change in Law affecting such qualification as a Clean Peak Resource) and (iii) tracked in the GIS to ensure a unit-specific accounting of the Delivery of the Energy to enable the Massachusetts Department of Environmental Protection to accurately account for such Energy in the state greenhouse gas emissions inventory, created under chapter 298 of the Acts of 2008, and the Facility shall have a Commercial Operation Date as verified by Buyer.

Title to Products.  Seller has and shall have good and marketable title to all Products sold and Delivered to Buyer under this Agreement, free and clear of all liens, charges and encumbrances.  Seller has not sold and, except as permitted in accordance with the terms of this Agreement, shall not sell any such Products to any other Person, and no Person other than Seller can claim an interest in any Product to be sold to Buyer under this Agreement.

Negotiations.  The terms and provisions of this Agreement are the result of arm’s length and good faith negotiations on the part of Seller and equal bargaining power of the Parties.  No principle of law or equity regarding construing ambiguities in this Agreement against the drafting Party shall apply.

Bankruptcy.  There are no bankruptcy, insolvency, reorganization, receivership or other such proceedings pending against or being contemplated by Seller, or, to Seller’s knowledge, threatened against it.

No Misrepresentations.  The reports and other submittals by Seller to Buyer under this Agreement are not false or misleading in any material respect.

No Default.  No Default or Event of Default has occurred and is continuing and no Default or Event of Default shall occur as a result of the performance by Seller of its obligations under this Agreement.

Site Control.  Seller (i) holds a federal lease issued on a competitive basis after January 1, 2012 for an offshore wind energy generation site located on the Outer Continental Shelf and for which no turbine is located within ten miles of any inhabited area, and Seller reasonably expects such lease to remain in full force and effect for the entire Term; and (ii) has either (a) has acquired all other real property rights to construct and operate the Facility, to interconnect the Facility to the Interconnecting Utility, to construct the Network Upgrades (to the extent it is Seller’s responsibility to do so) and to perform Seller’s obligations under this Agreement or (b) has an irrevocable option to acquire such other real property rights and the only condition upon Seller’s exercise of such option to acquire such real property rights is the payment of an amount that represents the fair market value of such real property rights.

Commitment Agreement.  Seller has executed the Commitment Agreement and the Commitment Agreement is in full force and effect.  A breach of or default under the Commitment Agreement after the Effective Date will not operate to create an Event of Default under this Agreement, unless the conduct producing the breach of or default under the Commitment Agreement would independently create an Event of Default under this Agreement.

Continuing Nature of Representations and Warranties.  The representations and warranties set forth in this Section are made as of the Effective Date and, except where otherwise stated, deemed made continually throughout the Term, subject to the removal of the references to the Regulatory Approval and Permits as and when the Regulatory Approval and Permits are obtained.  If at any time during the Term, a Party has knowledge of any event or information which causes any of the representations and warranties in this Article 7 to be untrue or misleading, such Party shall provide the other Party with prompt written notice of the event or information, the representations and warranties affected, and the corrective action such Party shall take.  The notice required pursuant to this Section shall be given as soon as practicable after the occurrence of each such event.

REGULATORY APPROVAL

Receipt of Regulatory Approval.  The obligations of the Parties to perform this Agreement, other than the Parties’ obligations under Section 3.3(d), Section 3.7, Section 6.1, Section 6.2, Section 8.2, and Section 12, are conditioned upon and shall not become effective or binding until the receipt of the Regulatory Approval.  Buyer shall notify Seller within ten (10) Business Days after receipt of the Regulatory Approval or receipt of a final written order of the MDPU regarding this Agreement that does not satisfy all of the requirements of the Regulatory Approval (except that the final written order may remain subject to appeal or rehearing).  This Agreement may be terminated by either Buyer or Seller in the event that Regulatory Approval is not received within 270 days after filing, without liability as a result of such termination, subject to the return of Credit Support as provided in Section 6.2.

Related Transmission Approvals.  The obligation of the Parties to perform this Agreement is further conditioned upon the receipt of any Related Transmission Approvals on or before _______.

BREACHES; REMEDIES

Events of Default by Either Party.  It shall constitute an event of default (“Event of Default”) by either Party hereunder if:

Representation or Warranty.  Any breach of any representation or warranty of such Party set forth herein, or in filings or reports made pursuant to this Agreement occurs, where such breach is not fully cured and corrected within thirty (30) days after the Non-Defaulting Party has provided written notice to the Defaulting Party; or

Payment Obligations.  Any undisputed payment due and payable hereunder is not made on the date due, and such failure continues for more than ten (10) Business Days after notice thereof is given by the Non-Defaulting Party to the Defaulting Party; or

Other Covenants.  Other than:

failure of the Facility to achieve the Commercial Operation Date by the Guaranteed Commercial Operation Date;

a Rejected Purchase; or

an Event of Default described in Section 9.1(a), 9.1(b), 9.1(d), 9.1(e) or 9.2,

such Party fails to perform, observe or otherwise to comply with any obligation hereunder and such failure continues for more than thirty (30) days after notice thereof is given by the Non-Defaulting Party to the Defaulting Party; provided, however, such period shall be extended for an additional period of up to thirty (30) days if, despite using commercially reasonable efforts,  the Defaulting Party is unable to cure within the initial thirty (30) day period so long as such cure is diligently pursued by the Defaulting Party until such Default had been corrected, but in any event shall be cured within sixty (60) days of the notice from the Non-Defaulting Party; or

Bankruptcy.  Such Party (i) is adjudged bankrupt or files a petition in voluntary bankruptcy under any provision of any bankruptcy law or consents to the filing of any bankruptcy or reorganization petition against such Party under any such law, or (without limiting the generality of the foregoing) files a petition to reorganize pursuant to 11 U.S.C. § 101 or any similar statute applicable to such Party, as now or hereinafter in effect, (ii) makes an assignment for the benefit of creditors, or admits in writing an inability to pay its debts generally as they become due, or consents to the appointment of a receiver or liquidator or trustee or assignee in bankruptcy or insolvency of such Party, or (iii) is subject to an order of a court of competent jurisdiction appointing a receiver or liquidator or custodian or trustee of such Party or of a major part of such Party’s property, which is not dismissed within sixty (60) days; or

Permit Compliance.  Such Party fails to obtain and maintain or cause to be obtained and maintained in full force and effect any Permit (other than the Regulatory Approval) necessary for such Party to perform its obligations under this Agreement

Events of Default by Seller.  In addition to the Events of Default described in Section 9.1, each of the following shall constitute an Event of Default by Seller hereunder if:

Taking of Facility Assets.  Other than with respect to a foreclosure on or other exercise by any Lender of any rights and remedy with respect to any asset of Seller in connection with a Financing, any asset of Seller that is required for the construction, operation or maintenance of the Facility or the performance of its obligations hereunder is taken upon execution or by other process of law directed against Seller, or any such asset is taken upon or subject to any attachment by any creditor of or claimant against Seller and such attachment is not disposed of within sixty (60) days after such attachment is levied; or

Failure to Maintain Credit Support.  The failure of Seller to provide, maintain and/or replenish the Development Period Security or the Operating Period Security as required pursuant to Article 6 of this Agreement, and such failure continues for more than five (5) Business Days after Buyer has provided written notice thereof to Seller.  For the avoidance of doubt, it shall be deemed an Event of Default if Seller provides Credit Support in the form of a letter of credit and, with respect to an outstanding letter of credit, one of the following events occurs with respect to the issuer of such letter of credit:  (i) such issuer shall fail to be a Qualified Bank; (ii) such issuer shall fail to comply with or perform its obligations under such letter of credit; or (iii) such issuer shall disaffirm, disclaim, repudiate or reject, in whole or in part, or challenge the validity of, such letter of credit, and such failure, disaffirmation, disclamation, repudiation or rejection continues for more than five (5) Business Days after Buyer has provided written notice thereof to Seller]; or

Energy Output.  The failure of the Facility to produce Energy for twelve (12) consecutive months during the Services Term,  except to the extent excused by (i) a Force Majeure, or (ii) a Catastrophic Failure not caused by a Force Majeure, unless and until such Catastrophic Failure exceeds the duration of the Catastrophic Failure Period; or

Failure to Satisfy ISO-NE Obligations.  The failure of Seller to satisfy, or cause to be satisfied (other than by Buyer), any material obligation under the ISO-NE Rules or ISO-NE Practices or any other obligation with respect to ISO-NE and such failure has an adverse effect on the Facility or Seller’s ability to perform its obligations under this Agreement or on Buyer or Buyer’s rights or  ability to receive the benefits under this Agreement; provided, however, if Seller’s failure to satisfy any obligation under the ISO-NE Rules or ISO-NE Practices does not have an adverse effect on Buyer or Buyer’s ability to receive the benefits under this Agreement, Seller shall have the opportunity to cure such failure within thirty (30) days of its occurrence; or

Failure to Meet Critical Milestones.  The failure of Seller to satisfy any Critical Milestone by the date set forth therefor in Section 3.1(a), as the same may be extended in accordance with Section 3.1(c); or

Abandonment.  On or after the Commercial Operation Date, the permanent relinquishment by Seller of all of its possession and control of the Facility, other than a transfer permitted under this Agreement; or

Assignment.  The assignment of this Agreement by Seller, or Seller’s sale or transfer of its interest (or any part thereof) in the Facility, except as permitted in accordance with Article 14; or

Delivery Failure.  The occurrence of a Delivery Failure on eleven (11) or more calendar days during the Services Term (except to the extent Energy was generated by the Facility and transmitted to the Delivery Point during the applicable time interval but not credited to the Buyer’s ISO-NE account and Seller has cured that failure through a corrective Internal Bilateral Transaction and transfer in the GIS in accordance with Section 4.3) (a corrective or resettlement IBT is an IBT through the ISO-NE data reconciliation process); or

Failure to Provide Status Reports.  A failure to provide timely, accurate and complete status reports in accordance with this Agreement, and such failure continues for more than five (5) days after notice thereof is given by Buyer; or

Failure to Maintain RPS Eligibility.  A failure to maintain RPS eligibility requirements except to the extent due to a change in Law as described in Section 4.1(b); or

Failure to Maintain CES Eligibility.  A failure to maintain CES eligibility requirements except to the extent due to a change in Law as described in Section 4.1(b); or

Failure to Maintain Clean Peak Standard Eligibility.  A failure to maintain Clean Peak Standard eligibility requirements except to the extent described in Section 4.1(b); or

Remedies.

Suspension of Performance and Remedies at Law.  Upon the occurrence and during the continuance of an Event of Default, the Non-Defaulting Party shall have the right, but not the obligation, to (i) withhold any payments due the Defaulting Party under this Agreement, (ii) suspend its performance hereunder, and (iii) exercise such other remedies as provided for in this Agreement including, without limitation, the termination right set forth in Section 9.3(b), and, to the extent not inconsistent with the terms of this Agreement, such remedies available at law and in equity.  In addition to the foregoing, except for breaches for which an express remedy or measure of damages is provided herein, the Non-Defaulting Party shall retain its right of specific performance to enforce the Defaulting Party’s obligations under this Agreement.

Termination and Termination Payment.  Upon the occurrence of an Event of Default, a Non-Defaulting Party may terminate this Agreement at its sole discretion by providing written notice of such termination to the Defaulting Party.  If the Non-Defaulting Party terminates this Agreement, it shall be entitled to calculate and receive as its sole remedy for such Event of Default a “Termination Payment” as follows:

Termination by Buyer Prior to Commercial Operation Date.  If Buyer terminates this Agreement because of an Event of Default by Seller occurring prior to the Commercial Operation Date, the Termination Payment due to Buyer shall be equal to the sum of (x) all Delay Damages due and owing by Seller through the date of such termination plus (y) the full amount of the Development Period Security required to be provided to Buyer by Seller.

Termination by Seller Prior to Commercial Operation Date.  If Seller terminates this Agreement because of an Event of Default by Buyer prior to the Commercial Operation Date, Seller shall only receive a Termination Payment if the Commercial Operation Date either occurs on or before the Guaranteed Commercial Operation Date or would have occurred by such date but for the Event of Default by Buyer giving rise to the termination of this Agreement.  In such case, (x) if Seller terminates this Agreement because of an Event of Default by Buyer prior to the Financial Closing Date, the Termination Payment due to Seller shall be equal to the lesser of:  (i) Buyer’s Percentage Entitlement to Seller’s out-of-pocket expenses incurred in connection with the development and construction of the Facility prior to such termination and for which Seller has provided adequate documentation to enable Buyer to verify the expense claimed, or (ii) the Termination Payment due to Seller as calculated according to the methodology in Section 9.3(b)(iv), as if the Commercial Operation Date had occurred prior to the date of the termination by Seller; and (y) if Seller terminates this Agreement because of an Event of Default by Buyer on or after the Financial Closing Date, the Termination Payment due to Seller shall be calculated according to the methodology in Section 9.3(b)(iv), as if the Commercial Operation Date had occurred prior to the date of the termination by Seller.

Termination by Buyer On or After Commercial Operation Date.  If Buyer terminates this Agreement because of an Event of Default by Seller occurring on or after the Commercial Operation Date, the Termination Payment due to Buyer shall be equal to the greater of:  (i) the security required to be provided in accordance with Article 6, or (ii) the amount, if positive, calculated according to the following formula:  (x) the present value, discounted at a rate equal to the prime rate specified in the “Money & Investing” section of The Wall Street Journal determined as of the date of the notice of default, plus 300 basis points, for each month remaining in the Services Term, of (A) the amount, if, any, by which the forward market price of Energy and RECs, as determined by the average of the quotes of at least two nationally recognized energy consulting firms or brokers chosen by Buyer, for Replacement Energy and Replacement RECs, exceeds the applicable Price that would have been paid pursuant to Exhibit D of this Agreement, multiplied by (B) Buyer’s Percentage Entitlement of the projected Energy output of the Facility as determined by a recognized  third party expert selected by Buyer, using a probability of exceedance basis of 50%; plus (y) any costs and losses incurred by Buyer as a result of the Event of Default and termination of the Agreement.

All such amounts shall be determined by Buyer in good faith and in a commercially reasonable manner, and Buyer shall provide Seller with a reasonably detailed calculation of the Termination Payment due under this Section 9.3(b)(iii).

Termination by Seller On or After Commercial Operation Date.  If Seller terminates this Agreement because of an Event of Default by Buyer occurring on or after the Commercial Operation Date, the Termination Payment due to Seller shall be equal to the amount, if positive, calculated according to the following formula:  (x) the present value, discounted at a rate equal to the prime rate specified in the “Money & Investing” section of The Wall Street Journal determined as of the date of the notice of default,  plus 300 basis points, for each month remaining in the Services Term, of (i) the amount, if, any, by which the applicable Price that would have been paid pursuant to  Exhibit D of this Agreement, exceeds the forward market price of Energy and RECs  as determined by the average of the quotes of at least two nationally recognized energy consulting firms or brokers chosen by Seller, for Replacement Energy and Replacement RECs,  multiplied by (ii) Buyer’s Percentage Entitlement to the projected Energy output of the Facility as determined by a recognized  third party expert selected by Seller using a probability of exceedance basis of 50%; plus, (y) any costs and losses incurred by Seller as a result of the Event of Default and termination of the Agreement.

All such amounts shall be determined by Seller in good faith and in a commercially reasonable manner, and Seller shall provide Buyer with a reasonably detailed calculation of the Termination Payment due under this Section 9.3(b)(iv).

Acceptability of Liquidated Damages.  Each Party agrees and acknowledges that (i) the damages and losses (including without limitation the loss of environmental, reliability and economic benefits contemplated under this Agreement) that the Parties would incur due to an Event of Default would be difficult or impossible to predict with certainty, and (ii) it is impractical and difficult to assess actual damages in the circumstances stated, and therefore the Termination Payment as agreed to by the Parties and set forth herein is a fair and reasonable calculation of such damages.

Payment of Termination Payment.  The Defaulting Party shall make the Termination Payment within ten (10) Business Days after such notice is effective, regardless whether the Termination Payment calculation is disputed.  If the Defaulting Party disputes the Non-Defaulting Party’s calculation of the Termination Payment, in whole or in part, the Defaulting Party shall within ten (10) Business Days of receipt of the calculation of the Termination Payment, provide to the Non-Defaulting Party a detailed written explanation of the basis for such dispute.  If the Parties are unable to resolve the dispute within thirty (30) days, Article 11 shall apply.

Set-off.  The Non-Defaulting Party shall be entitled, at its option and in its discretion, to withhold and set off any amounts owed by the Non-Defaulting Party to the Defaulting Party against any payments and any other amounts owed by the Defaulting Party to the Non-Defaulting Party, including any Termination Payment payable as a result of any early termination of this Agreement.

Notice to Lender and Tax Equity Investor.  Seller shall provide Buyer with a notice identifying a single Lender and a single Tax Equity Investor (if any) to whom default notices are to be issued.  Buyer shall provide a copy of the notice of any default of Seller under this Article 9 to such Lender, and Buyer shall afford such Lender the same opportunities to cure Events of Default under this Agreement as are provided to Seller hereunder.

Limitation of Remedies, Liability and Damages.  EXCEPT AS EXPRESSLY SET FORTH HEREIN, THERE IS NO WARRANTY OF MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE, AND ANY AND ALL IMPLIED WARRANTIES ARE DISCLAIMED.  THE PARTIES CONFIRM THAT THE EXPRESS REMEDIES AND MEASURES OF DAMAGES PROVIDED IN THIS AGREEMENT SATISFY THE ESSENTIAL PURPOSES HEREOF.  FOR BREACH OF ANY PROVISION FOR WHICH AN EXPRESS REMEDY OR MEASURE OF DAMAGES IS PROVIDED, SUCH EXPRESS REMEDY OR MEASURE OF DAMAGES SHALL BE THE SOLE AND EXCLUSIVE REMEDY, THE OBLIGOR’S LIABILITY SHALL BE LIMITED AS SET FORTH IN SUCH PROVISION AND ALL OTHER REMEDIES OR DAMAGES AT LAW OR IN EQUITY ARE WAIVED.  IF NO REMEDY OR MEASURE OF DAMAGES IS EXPRESSLY PROVIDED HEREIN, THE OBLIGOR’S LIABILITY SHALL BE LIMITED TO DIRECT ACTUAL DAMAGES ONLY, SUCH DIRECT ACTUAL DAMAGES SHALL BE THE SOLE AND EXCLUSIVE REMEDY, AND ALL OTHER REMEDIES OR DAMAGES AT LAW OR IN EQUITY ARE WAIVED.  UNLESS EXPRESSLY HEREIN PROVIDED, NEITHER PARTY SHALL BE LIABLE FOR CONSEQUENTIAL, INCIDENTAL, PUNITIVE, EXEMPLARY OR INDIRECT DAMAGES, LOST PROFITS OR OTHER BUSINESS INTERRUPTION DAMAGES, BY STATUTE, IN TORT OR CONTRACT, UNDER ANY INDEMNITY PROVISION OR OTHERWISE.  TO THE EXTENT ANY DAMAGES REQUIRED TO BE PAID HEREUNDER ARE LIQUIDATED, THE PARTIES ACKNOWLEDGE THAT THE DAMAGES ARE DIFFICULT OR IMPOSSIBLE TO DETERMINE, OR OTHERWISE OBTAINING AN ADEQUATE REMEDY IS INCONVENIENT AND THE DAMAGES CALCULATED HEREUNDER CONSTITUTE A REASONABLE APPROXIMATION OF THE HARM OR LOSS.

FORCE MAJEURE

Force Majeure.

The term “Force Majeure” means an unusual, unexpected and significant event:  (i) that was not within the control of the Party claiming its occurrence; (ii) that could not have been prevented or avoided by such Party through the exercise of reasonable diligence; and (iii) that directly prohibits or prevents such Party from performing its obligations under this Agreement.  Under no circumstances shall Force Majeure include (v) any full or partial curtailment in the electric output of the Facility that is caused by or arises from a mechanical or equipment breakdown or other mishap or events or conditions attributable to normal wear and tear or flaws, unless such curtailment or mishap is caused by one of the following:  acts of God such as floods, hurricanes or tornados; sabotage; terrorism; war; or the mechanical breakdown of onshore repair facilities,, (w) any occurrence or event that merely increases the costs or causes an economic hardship to a Party, (x) any occurrence or event that was caused by or contributed to by the Party claiming the Force Majeure, (y) Seller’s ability to sell the Products at a price greater than that set out in this Agreement, or (z) Buyer’s ability to procure the Products at a price lower than that set out in this Agreement.  In addition, a delay or inability to perform attributable to a Party’s lack of preparation, a Party’s failure to timely obtain and maintain all necessary Permits (excepting the Regulatory Approval) or qualifications, any delay or failure in satisfying the Critical Milestone obligations specified in Section 3.1(a)(iii) and (vii) (Permits) or Section 3.1(a)(v) (Financing), a failure to satisfy contractual conditions or commitments, or lack of or deficiency in funding or other resources shall each not constitute a Force Majeure or be the basis for a claim of Force Majeure.  Neither Party may raise a claim of Force Majeure based in whole or in part on curtailment by a Transmission Provider unless (i) such Party has contracted for firm transmission with a Transmission Provider for the Products to be delivered to or received at the Delivery Point and (ii) such curtailment is due to “force majeure” or “uncontrollable force” or a similar term as defined under the Transmission Provider’s tariff; provided, however, that existence of the foregoing factors shall not be sufficient to conclusively or presumptively prove the existence of a Force Majeure absent a showing of other facts and circumstances which in the aggregate with such factors establish that a Force Majeure as defined herein has occurred.

Subject to Section 3.1(d), if either Party is unable, wholly or in part, by Force Majeure to perform obligations under this Agreement, such performance shall be excused and suspended so long as the circumstances that give rise to such inability exist or would exist if the Party claiming the Force Majeure used commercially reasonable efforts to cure such circumstances, but for no longer period.  The Party whose performance is affected shall give prompt notice thereof; such notice may be given orally or in writing but, if given orally, it shall be promptly confirmed in writing, providing details regarding the nature, extent and expected duration of the Force Majeure, its anticipated effect on the ability of such Party to perform obligations under this Agreement, and the estimated duration of any interruption in service or other adverse effects resulting from such Force Majeure, and shall be updated or supplemented to keep the other Party advised of the effect and remedial measures being undertaken to overcome the Force Majeure.  Such inability shall be promptly corrected to the extent it may be corrected through the exercise of due diligence.  Neither party shall be liable for any losses or damages arising out of a suspension of performance that occurs because of Force Majeure.

Notwithstanding the foregoing and subject to Section 3.1(f), if the Force Majeure prevents full or partial performance under this Agreement for a period of twenty-four (24) months or more, the Party whose performance is not prevented by Force Majeure shall have the right to terminate this Agreement upon written notice to the other Party and without further recourse (and without regard to whether an Event of Default has occurred under Section 9.2(c)).  In no event will any delay or failure of performance caused by any conditions or events of Force Majeure extend this Agreement beyond its stated Term.

DISPUTE RESOLUTION

Dispute Resolution.  In the event of any dispute, controversy or claim between the Parties arising out of or relating to this Agreement (collectively, a “Dispute”), in addition to any other remedies provided hereunder, the Parties shall attempt to resolve such Dispute through consultations between the Parties.  If the Dispute has not been resolved within fifteen (15) Business Days after such consultations between the Parties, then either Party may seek to resolve such Dispute in the courts of the Commonwealth of Massachusetts; provided, however, if the Dispute is subject to FERC’s jurisdiction over wholesale power contracts, then either Party may elect to proceed with the mediation through FERC’s Dispute Resolution Service; provided, however, that if one Party fails to participate in the negotiations as provided in this Section 11.1, the other Party can initiate mediation prior to the expiration of the fifteen (15) Business Days.  Unless otherwise agreed, the Parties will select a mediator from the FERC panel.  The Parties may, by written agreement signed by both Parties, alter any time deadline, location(s) for meeting(s), or procedure outlined herein or in FERC’s rules for mediation.  The procedure specified herein shall be the sole and exclusive procedure for the resolution of Disputes.  To the fullest extent permitted by law, any mediation proceeding and any settlement shall be maintained in confidence by the Parties.

Allocation of Dispute Costs.  The fees and expenses associated with mediation shall be divided equally between the Parties, and each Party shall be responsible for its own legal fees, including but not limited to attorney fees, associated with any Dispute.

Consent to Jurisdiction.  Subject to Section 11.1, the Parties agree to the exclusive jurisdiction of the state and federal courts located in the Commonwealth of Massachusetts for any legal proceedings that may be brought by a Party arising out of or in connection with any Dispute.

Waiver of Jury Trial and Inconvenient Forum Claim.  EACH PARTY HEREBY WAIVES TO THE FULLEST EXTENT PERMITTED BY LAW ANY RIGHT IT MAY HAVE TO A TRIAL BY JURY IN RESPECT OF ANY SUIT, ACTION OR PROCEEDING ARISING OUT OF, RESULTING FROM OR IN ANY WAY RELATING TO THIS AGREEMENT.  BOTH PARTIES IRREVOCABLY WAIVE, TO THE FULLEST EXTENT PERMITTED BY LAW, ANY OBJECTION THAT THEY MAY NOW OR HEREAFTER HAVE TO THE LAYING OF VENUE AS SET FORTH IN THIS ARTICLE 11 AND ANY CLAIM THAT ANY SUCH PROCEEDING HAS BEEN BROUGHT IN ANY INCONVENIENT FORUM.

CONFIDENTIALITY

Nondisclosure.  Buyer and Seller each agrees not to disclose to any Person and to keep confidential, and to cause and instruct its Affiliates, officers, directors, employees, partners and representatives not to disclose to any Person and to keep confidential, any non-public information relating to the terms and provisions of this Agreement, and any information relating to the Products to be supplied by Seller hereunder, and such other non-public information that is designated as “Confidential.”  Notwithstanding the foregoing, any such information may be disclosed:

to the extent Buyer determines it is appropriate in connection with efforts to obtain or maintain the Regulatory Approval or to seek rate recovery for amounts expended by Buyer under this Agreement

as required by applicable laws, regulations, filing requirements, rules or orders or by any subpoena or similar legal process of any Governmental Entity so long as the disclosing Party gives the non-disclosing Party written notice at least three (3) Business Days prior to such disclosure, if practicable;

to the Affiliates of either Party and to the consultants, attorneys, auditors, financial advisors, lenders or potential lenders and their advisors of either Party or their Affiliates, but solely to the extent they have a need to know that information;

in order to comply with any rule or regulation of ISO-NE, other system operators, any stock exchange or similar Person or for financial disclosure purposes;

to the extent the non-disclosing Party shall have consented in writing prior to any such disclosure; and

to the extent that the information was previously made publicly available other than as a result of a breach of this Section 12.1;

provided, however, in each case, that the Party seeking such disclosure shall, to the extent practicable, use commercially reasonable efforts to prevent or limit the disclosure.  The Parties shall be entitled to all remedies available at law or in equity to enforce or seek relief in connection with this Section 12.1.

Public Statements.  No public statement, press release or other voluntary publication regarding this Agreement or the transactions to be made hereunder shall be made or issued without the prior consent of the other Party.

INDEMNIFICATION

Indemnification Obligations.  Seller shall indemnify, defend and hold Buyer and its partners, shareholders, directors, officers, employees and agents (including, but not limited to, Affiliates and contractors and their employees), harmless from and against all liabilities, damages, losses, penalties, claims, demands, suits and proceedings of any nature whatsoever arising from or related to Seller’s execution, delivery or performance of this Agreement, or Seller’s negligence, gross negligence, or willful misconduct, or Seller’s failure to satisfy any obligation or liability under this Agreement, or Seller’s failure to satisfy any regulatory requirement or commitment associated with this Agreement.

Failure to Defend.  If Seller fails to assume the defense of a claim meriting indemnification, Buyer may at the expense of Seller contest, settle or pay such claim, and shall promptly reimburse Buyer for all costs incurred by Buyer associated therewith.

ASSIGNMENT AND CHANGE OF CONTROL

Prohibition on Assignments.  Except as permitted under this Article 14, this Agreement (and any portion thereof) may not be assigned by either Party without the prior written consent of the other Party, which consent may not be unreasonably withheld, conditioned or delayed.  The Party requesting the other Party’s consent to an assignment of this Agreement will reimburse such other Party for all “out of pocket” costs and expenses such other Party incurs in connection with that consent, without regard to whether such consent is provided.  When assignable, this Agreement shall be binding upon, shall inure to the benefit of, and may be performed by, the successors and assignees of the Parties, except that no assignment, pledge or other transfer of this Agreement by either Party shall operate to release the assignor, pledgor, or transferor from any of its obligations under this Agreement (and shall not impair any Credit Support given by Seller hereunder) unless the other Party (or its successors or assigns) consents in writing to the assignment, pledge or other transfer and expressly releases the assignor, pledgor, or transferor from its obligations thereunder.

Permitted Assignment by Seller.  Buyer’s consent shall not be required for Seller to pledge or assign the Facility, this Agreement or the revenues under this Agreement to any Lender as security for any Financing of the Facility; provided, however, if Seller requests Buyer’s consent to such an assignment, (i) Buyer shall provide that consent subject to Buyer’s execution of a consent to assignment in a form acceptable to Buyer and Seller, and (ii) Seller will reimburse Buyer for all “out of pocket” costs and expenses Buyer incurs in connection with that consent, without regarding to whether such consent is provided.

Change in Control over Seller.  Buyer’s consent shall be required for any change in Control over Seller, which consent shall not be unreasonably withheld, conditioned or delayed and shall be provided if Buyer reasonably determines that such change in Control does not have a material adverse effect on Seller’s creditworthiness or Seller’s ability to perform its obligations under this Agreement.

Permitted Assignment by Buyer.  Buyer shall have the right to assign this Agreement without consent of Seller (a) in connection with any merger or consolidation of Buyer with or into another Person or any exchange of all of the common stock or other equity interests of Buyer or Buyer’s parent for cash, securities or other property or any acquisition, reorganization, or other similar corporate transaction involving all or substantially all of the common stock or other equity interests in, or assets of, Buyer, or (b) to any substitute purchaser of the Products so long as in the case of either clause (a) or clause (b) of this Section 14.4, either (1) the proposed assignee’s credit rating is at least either BBB- from S&P or Baa3 from Moody’s or (2) the proposed assignee’s credit rating is equal to or better than that of Buyer at the time of the proposed assignment, or (3) such assignment, or in the case of clause (a) above the transaction associated with such assignment, has been approved by the MDPU or the appropriate Governmental Entity.

Prohibited Assignments.  Any purported assignment of this Agreement not in compliance with the provisions of this Article 14 shall be null and void.

TITLE; RISK OF LOSS

Title to and risk of loss related to Buyer’s Percentage Entitlement of the Energy shall transfer from Seller to Buyer at the Delivery Point.  Title and risk of loss related to Buyer’s Percentage Entitlement of the RECs shall transfer to Buyer when the same are credited to Buyer’s GIS account(s) or the GIS account(s) designated by Buyer to Seller in writing.  Seller warrants that it shall deliver to Buyer the Products free and clear of all liens and claims therein or thereto by any Person.

AUDIT

Audit.  Each Party shall have the right, upon reasonable advance notice, and at its sole expense (unless the other Party has defaulted under this Agreement, in which case the Defaulting Party shall bear the expense) and during normal working hours, to examine the records of the other Party to the extent reasonably necessary to verify the accuracy of any statement, charge or computation made pursuant to this Agreement.  If requested, a Party shall provide to the other Party additional information documenting the quantities of Products delivered or provided hereunder.  If any such examination reveals any overcharge, the necessary adjustments in such statement and the payments thereof shall be made promptly and shall include interest at the Late Payment Rate from the date the overpayment was made until credited or paid.

Access to Financial Information.  Seller shall provide to Buyer within fifteen (15) days of receipt of Buyer’s written request financial information and statements applicable to Seller as well as access to financial personnel, so that Buyer may address any inquiries relating to Seller’s financial resources.

NOTICES

Any notice or communication given pursuant hereto shall be in writing and (1) delivered personally (personally delivered notices shall be deemed given upon written acknowledgment of receipt after delivery to the address specified or upon refusal of receipt); or (2) mailed by registered or certified mail, postage prepaid (mailed notices shall be deemed given on the actual date of delivery, as set forth in the return receipt, or upon refusal of receipt); or (3) delivered by fax or electronic mail (notices sent by fax or electronic mail shall be deemed given upon confirmation of delivery); or (4) by reputable overnight courier; in each case addressed as follows or to such other addresses as may hereafter be designated by either Party to the other in writing:

If to Buyer:	[	]

With a copy to:	[	]

If to Seller:	[	]

With a copy to:	[	]

WAIVER AND MODIFICATION

This Agreement may be amended and its provisions and the effects thereof waived only by a writing executed by the Parties, and no subsequent conduct of any Party or course of dealings between the Parties shall effect or be deemed to effect any such amendment or waiver.  No waiver of any of the provisions of this Agreement shall be deemed or shall constitute a waiver of any other provision hereof (whether or not similar), nor shall such waiver constitute a continuing waiver unless otherwise expressly provided.  The failure of either Party to enforce any provision of this Agreement shall not be construed as a waiver of or acquiescence in or to such provision.  Buyer shall determine in its sole discretion whether any amendment or waiver of the provisions of this Agreement shall require Regulatory Approval or MDPU filing and/or approval.  If Buyer determines that any such approval or filing is required, then such amendment or waiver shall not become effective unless and until Regulatory Approval or such other approval is received, or such MDPU filing is made and any requested MDPU approval is received.

INTERPRETATION

Choice of Law.  Interpretation and performance of this Agreement shall be in accordance with, and shall be controlled by, the laws of the Commonwealth of Massachusetts (without regard to its principles of conflicts of law).

Headings.  Article and Section headings are for convenience only and shall not affect the interpretation of this Agreement.  References to articles, sections and exhibits are, unless the context otherwise requires, references to articles, sections and exhibits of this Agreement.  The words “hereof” and “hereunder” shall refer to this Agreement as a whole and not to any particular provision of this Agreement.

Forward Contract.  The Parties acknowledge and agree that this Agreement and the transactions contemplated hereunder are a “forward contract” within the meaning of the United States Bankruptcy Code.

Standard of Review.  The Parties acknowledge and agree that the standard of review for any avoidance, breach, rejection, termination or other cessation of performance of or changes to any portion of this integrated, non-severable Agreement (as described in Section 22) over which FERC has jurisdiction, whether proposed by Seller, by Buyer, by a non-party of, by FERC acting sua sponte shall be the “public interest” standard of review set forth in United Gas Pipe Line Co. v. Mobile Gas Serv. Co., 350 U.S. 332 (1956) and Federal Power Comm’n v. Sierra Pac. Power Co., 350 U.S. 348 (1956).  Each Party agrees that if it seeks to amend any applicable power sales tariff during the Term, such amendment shall not in any way materially and adversely affect this Agreement without the prior written consent of the other Party.  Each Party further agrees that it shall not assert, or defend itself, on the basis that any applicable tariff is inconsistent with this Agreement.

Change in ISO-NE Rules and ISO-NE Practices.  This Agreement is subject to the ISO-NE Rules and ISO-NE Practices.  If, during the Term of this Agreement, any ISO-NE Rule or ISO-NE Practice is terminated, modified or amended or is otherwise no longer applicable, resulting in a material alteration of a material right or obligation of a Party hereunder, the Parties agree to negotiate in good faith in an attempt to amend or clarify this Agreement to embody the Parties’ original intent regarding their respective rights and obligations under this Agreement, provided that neither Party shall have any obligation to agree to any particular amendment or clarification of this Agreement.  The intent of the Parties is that any such amendment or clarification reflect, as closely as possible, the intent, substance and effect of the ISO-NE Rule or ISO-NE Practice being replaced, modified, amended or made inapplicable as such ISO-NE Rule or ISO-NE Practice was in effect prior to such termination, modification, amendment, or inapplicability, provided that such amendment or clarification shall not in any event alter (i) the purchase and sale obligations of the Parties pursuant to this Agreement, or (ii) the Price .

Dodd Frank Act Representations.  The Parties agree that this Agreement (including all transactions reflected herein) is not a “swap” within the meaning of the Commodity Exchange Act (“CEA”) and the rules, interpretations and other guidance of the Commodity Futures Trading Commission (“CFTC Rules”), and that the primary intent of this Agreement is physical settlement (i.e., actual transfer of ownership) of the nonfinancial commodity and not solely to transfer price risk.  In reliance upon such agreement, each Party represents to the other that:

With respect to the commodity to be purchased and sold hereunder, it is a commercial market participant, a commercial entity and a commercial party, as such terms are used in the CFTC Rules, and it is a producer, processor, or commercial user of, or a merchant handling, the commodity and it is entering into this Agreement for purposes related to its business as such;

It is not registered or required to be registered under the CFTC Rules as a swap dealer or a major swap participant;

It has entered into this Agreement in connection with the conduct of its regular business and it has the capacity or ability to regularly make or take delivery of the commodity to be purchased and sold hereunder;

With respect to the commodity to be purchased and sold hereunder, it intends to make or take physical delivery of the commodity;

At the time that the Parties enter into this Agreement, any embedded volumetric optionality in this Agreement is primarily intended by the holder of such option or optionality to address physical factors or regulatory requirements that reasonably influence demand for, or supply of, the commodity to be purchased and sold hereunder;

With respect to any embedded commodity option in this Agreement, such option is intended to be physically settled so that, if exercised, the option would result in the sale of the commodity to be purchased or sold hereunder for immediate or deferred shipment or delivery; and

The commodity to be purchased and sold hereunder is a nonfinancial commodity, and is also an exempt commodity or an agricultural commodity, as such terms are defined and interpreted in the CFTC Rules.

To the extent that reporting of any transactions related to this Agreement is required by the CFTC Rules, the Parties agree that Seller shall be responsible for such reporting (the “Reporting Party”).  The Reporting Party’s reporting obligations shall continue until the reporting obligation has expired or has been terminated in accordance with CFTC rules.  Buyer, as the Party that is not undertaking the reporting obligations shall timely provide the Reporting Party all necessary information requested by the Reporting Party for it to comply with CFTC rules.

Change in Law or Buyer’s Accounting Treatment, Subsequent Judicial or Regulatory Action.

    - If, during the Term of this Agreement, there is a change in Law or accounting standards or rules or a change in the interpretation or applicability thereof that would result in adverse balance sheet or creditworthiness impacts on Buyer associated with this Agreement or the amounts paid for Products purchased hereunder, Buyer shall prepare an amendment to this Agreement to avoid or mitigate such impacts.  Buyer shall use commercially reasonable efforts to prepare such amendment in a manner that mitigates any material adverse effect(s) on Seller (as identified by Seller, acting reasonably) that could reasonably be expected to result from such amendment, but only to the extent that such mitigation can be accomplished in a manner that is consistent with the purpose of such amendment.  Seller agrees to execute such amendment provided that such amendment does not (unless Seller otherwise agrees) alter:  (i) the purchase and sale obligations of the Parties pursuant to this Agreement, or (ii) the Price.

    - Upon a determination by a court or regulatory body having jurisdiction over this Agreement or any of the Parties hereto, or over the establishment and enforcement of any of the statutes or regulations or orders or actions of regulatory agencies (including the MDPU) supporting this Agreement or the rights or obligations of the Parties hereunder that any of the statutes or regulations supporting this Agreement or the rights or obligations of the Parties hereunder, or orders of or actions of regulatory agencies (including the MDPU) implementing such statutes or regulations, or this Agreement on its face or as applied, violates any Law (including the State or Federal Constitution) (an “Adverse Determination”), each Party shall have the right to suspend performance under this Agreement without liability.  Seller may deliver and sell Products to a third party during any period of time for which Buyer suspends payments or purchases under this Section.  Upon an Adverse Determination becoming final and non-appealable, this Agreement shall be rendered null and void.

COUNTERPARTS; FACSIMILE OR PDF SIGNATURES

Any number of counterparts of this Agreement may be executed, and each shall have the same force and effect as an original.  Facsimile or PDF signatures hereon or on any notice or other instrument delivered under this Agreement shall have the same force and effect as original signatures.

NO DUTY TO THIRD PARTIES

Except as provided in any consent to assignment of this Agreement, nothing in this Agreement nor any action taken hereunder shall be construed to create any duty, liability or standard of care to any Person not a Party to this Agreement.

SEVERABILITY

Except as provided in Article 8, Section 19.5 or Section 19.7 hereof, if any term or provision of this Agreement or the interpretation or application of any term or provision to any prior circumstance is held to be unenforceable, illegal or invalid by a court or agency of competent jurisdiction, the remainder of this Agreement and the interpretation or application of all other terms or provisions to Persons or circumstances other than those which are unenforceable, illegal or invalid shall not be affected thereby, and each term and provision shall be valid and be enforced to the fullest extent permitted by law so long as all essential terms and conditions of this Agreement for both Parties remain valid, binding and enforceable and have not been declared to be unenforceable, illegal or invalid by a Governmental Entity of competent jurisdiction.  The Parties acknowledge and agree that essential terms and conditions of this Agreement for each Party include, without limitation, all pricing and payment terms and conditions of this Agreement, and that the essential terms and conditions of this Agreement for Buyer also include, without limitation, the terms and conditions of Section 19.7 of this Agreement.

INDEPENDENT CONTRACTOR

Nothing in this Agreement shall be construed as creating any relationship between Buyer and Seller other than that of Seller as independent contractor for the sale of Products, and Buyer as principal and purchaser of the same.  Neither Party shall be deemed to be the agent of the other Party for any purpose by reason of this Agreement, and no partnership or joint venture or fiduciary relationship between the Parties is intended to be created hereby.  Nothing in this Agreement shall be construed as creating any relationship between Buyer and the Interconnecting Utility.

ENTIRE AGREEMENT

This Agreement shall constitute the entire agreement and understanding between the Parties hereto and shall supersede all prior agreements and communications.

[Signature page follows]

IN WITNESS WHEREOF, each of Buyer and Seller has caused this Agreement to be duly executed on its behalf as of the date first above written.

[Buyer]

By:		
	Name:
	Title:

[Seller]

By:		
	Name:
	Title:

EXHIBIT A

DESCRIPTION OF FACILITY

Facility:  [Note to Bidder:  Describe fully the offshore wind facility with reference to plans showing layout of the facilities, including number and location of turbines and related facilities]

Delivery Point:  [Note to Bidder:  When specifying the Delivery Point in this Exhibit A, this location should be defined as a PTF node such that the EDCs are not responsible for wheeling charges or other related charges (e.g., transmission interconnection, service and delivery charges, including all related administrative fees and other charges in connection with the Delivery of Energy to the Delivery Point).]

ISO-NE PTF Node:  ____________________________________________

Proposed Facility Size:  (Nameplate capacity of the Facility as provided with bid, expressed in MWs [AC])

EXHIBIT B

SELLER’S CRITICAL MILESTONES

[To be prepared to conform with the Critical Milestones referenced in Section 3.1]

EXHIBIT C

FORM OF PROGRESS REPORT

Each Progress Report after the initial report shall include a redline against the previous quarter’s report and shall include the following items:

- A brief Facility description.

- The indicative site plan of the Facility.

- A description of any changes to the Facility or site plan.

- A bar chart schedule showing progress on achieving each Critical Milestone, including progress on achieving the Commercial Operation Date.

- A PERT or GANTT chart showing the critical path schedule of major items and activities regarding the development, construction and startup of the Facility.

- A summary of major activities during the previous quarter.

- A description of major activities scheduled for the current quarter.

- A description of the progress on achieving each Critical Milestone.

- A description of issues that have adversely impacted or could reasonably be expected to adversely impact achievement of any Critical Milestone, including a description of any events that have resulted in or could reasonably be expected to result in delays.

The Parties intend that, within five (5) to ten (10) days after each Progress Report is delivered to Buyer, a telephone call will be set up during business hours and upon reasonable notice to Seller to permit Buyer and its advisors and consultants to discuss such report with Seller and its advisors and consultants.  Consistent with Section 7.2(k) of this Agreement, the intent of both the Progress Reports and the telephone calls will be to provide Buyer with accurate, timely and reasonably detailed information, when taken as a whole, regarding the status and progress of, and any major problems associated with, the development and construction of the Facility as of the date furnished.

[Attach Documentation supporting any claim that a Critical Milestone has been achieved]

EXHIBIT D

PRODUCTS AND PRICING

1.	Price for Buyer’s Percentage Entitlement of Products.  The Price for the Buyer’s Percentage Entitlement of Delivered Products in nominal dollars shall be as follow:

(a)	Product Price - Commencing on the Commercial Operation Date, the Price per MWH for the Products shall be [equal to [$__] per MWh] [as follows].  [The Price per MWh for each billing period shall be allocated between Energy and RECs as follows]:

[If single Energy price and single REC price are provided for the contract term.]

[(i)	Energy  =	[amount bid by Seller]

(ii)	RECs  =	[amount bid by Seller]].

•	Fixed Contract Price [applicable to all technologies]

| Year |  | Energy Price ($/MWh) | REC Price ($/REC) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |
| 11 |  |  |  |
| 12 |  |  |  |
| 13 |  |  |  |
| 14 |  |  |  |
| 15 |  |  |  |
| 16 |  |  |  |
| 17 |  |  |  |
| 18 |  |  |  |
| 19 |  |  |  |
| 20 |  |  |  |

If the market price at the Delivery Point in the Real Time or Day Ahead markets, as applicable, for Energy Delivered by Seller is negative in any hour, the payment to Seller for deliveries of Energy shall be reduced by the difference between the absolute value of the hourly LMP at the Delivery Point and $0.00 per MWh for that Energy for each such hour.  Each monthly invoice shall reflect a reduction for all hours in the applicable month in which the LMP for the Energy at the Delivery Point is less than $0.00 per MWh.

Examples.  If delivered Energy equals 1 MWh and Price equals $50.00/MWh:

LMP at the Delivery Point equals (or is greater than) $0.00/MWh
Buyer payment of Price to Seller		$50.00
Seller credit/reimbursement for negative LMP to Buyer	  $0.00
Net Result:  Buyer pays Seller $50 for that hour

LMP at the Delivery Point equals -$150.00/MWh
Buyer payment of Price to Seller		  $50.00
Seller credit/reimbursement for negative LMP to Buyer	$150.00
Net Result:  Seller credits or reimburses Buyer $100 for that hour

EXHIBIT E

RELATED TRANSMISSION FACILITIES

EXHIBIT F

REQUIRED NETWORK UPGRADES

[NTD:  To be included in this exhibit are those Network Upgrades identified by the bidder in its Bid in order to achieve the Energy deliveries projected in the Bid, separate from those necessary for Seller’s satisfaction of the obligations under Section 3.7]

EXHIBIT G

FORM OF COMMITMENT AGREEMENT

Voluntary Agreement Commitment Agreement

This Voluntary Agreement Commitment Agreement (“Commitment Agreement”), dated  ________, is made and entered into by [Bidder], (“Successful Bidder”) for the benefit of [EDC] (“Distribution Company”). Successful Bidder and Distribution Company are hereinafter sometimes also referred to collectively as the “Parties.”

WITNESSETH

WHEREAS, Successful Bidder has been conditionally selected by Distribution Company as a winning bidder under the Request for Proposals for Long-Term Contracts for Offshore Wind Energy Projects, dated ____ (the “RFP”);

WHEREAS, concurrently with the execution and delivery of this Commitment Agreement, Successful Bidder has entered into a power purchase agreement with Distribution Company (“PPA”);

WHEREAS, as part of its performance under the PPA, Successful Bidder intends to construct, or cause to be constructed, Interconnection Customer Interconnection Facilities, as defined herein;

WHEREAS, Distribution Company and Successful Bidder desire to reasonably minimize obstacles to the ability of future offshore wind energy developers to deliver their energy and capacity to the onshore transmission system, possibly via interconnection with Successful Bidder’s ICIF;

NOW, THEREFORE, in consideration of the foregoing, and other good and valuable consideration the receipt and sufficiency of which are hereby acknowledged, and intending to be legally bound hereby, Successful Bidder hereby agrees as follows:

- Definitions

The following definitions shall apply to the provisions of this Commitment Agreement:

  - “Interconnection Customer’s Interconnection Facilities” (“ICIF”) means all facilities and equipment located between Successful Bidder’s offshore wind energy generation facilities collector system step-up transformers and the point of change of ownership at the onshore interconnection, including any modification, addition, or upgrades to such facilities and equipment, which facilities and equipment are constructed to physically and electrically interconnect Successful Bidder’s offshore wind energy generation facilities to the onshore transmission system.

  - “Third-Party Offshore Wind Developer” means any entity (other than Successful Bidder) developing offshore wind energy generation or delivery facilities and seeking interconnection to and/or delivery service on Successful Bidder’s ICIF pursuant to this Commitment Agreement

  - “Voluntary Agreement” means a voluntary agreement as contemplated in Federal Energy Regulatory Commission (“FERC”) Order No. 807, PP 117-18, to be entered into if a Third-Party Offshore Wind Developer requests studies and potential expansion of Successful Bidder’s ICIF to accommodate third party interconnection and delivery service, without the need for said third party to pursue its rights in the first instance via Sections 210, 211, and 212 of the Federal Power Act (“FPA”).

- In the event one or more Third-Party Offshore Wind Developers request  interconnection to and/or delivery service on Successful Bidder’s ICIF, Successful Bidder will study the requested interconnection and/or delivery service, provided that the Third-Party Offshore Wind Developer(s) agrees to pay the cost of such studies.

- Successful Bidder will negotiate in good faith and use commercially reasonable best efforts to conclude a Voluntary Agreement with any such Third-Party Offshore Wind Developer regarding expansion of, interconnection to, and delivery service over Successful Bidder’s ICIF to accommodate the Third-Party Offshore Wind Developer’s request.

- The Voluntary Agreement will incorporate interconnection and other provisions at least as  favorable to said Third-Party Offshore Wind Developers as the provisions of ISO New England Inc. (“ISO-NE”) Open Access Transmission Tariff Schedules 22 and 23 are to requesters of interconnection service seeking to connect to facilities subject to the ISO-NE interconnection procedures in those schedules.  Successful Bidder will respond to reasonable requests from ISO-NE or Third-Party Offshore Wind Developers for information deemed necessary to support an ISO-NE interconnection request by Third- Party Offshore Wind Developers on the ISO-NE system.

- If, after good faith attempts to conclude a Voluntary Agreement using commercially reasonable best efforts, Successful Bidder and Third-Party Offshore Wind Developer are unable to conclude such a Voluntary Agreement, Successful Bidder shall be relieved of any further obligations as to that Third-Party Offshore Wind Developer under this Commitment Agreement, and in such event, nothing herein shall diminish Third-Party Offshore Wind Developer’s rights independent of this Commitment Agreement to request relief from FERC.

- Third-Party Offshore Wind Developer may at any time exercise its rights under Federal Power Act Sections 206 or Sections 210, 211, and 212 that exist independent of this Commitment Agreement to file with FERC requesting an order requiring interconnection and/or delivery service on Successful Bidder’s ICIF.  In the event that the Third-Party Offshore Wind Developer exercises such rights, Successful Bidder will have no further obligations to such Third-Party Offshore Wind Developer under this Commitment Agreement.

- If an entity other than Successful Bidder obtains ownership or successor rights in Successful Bidder’s ICIF, Successful Bidder will ensure that such other entity as well as Successful Bidder will be bound by the terms and conditions of this Commitment Agreement.

- This Commitment Agreement is not intended to, and does not create any rights or obligations in either of the Parties or any other entity except for those rights or obligations explicitly identified herein, nor does this Commitment Agreement affect Successful Bidder’s rights under Order Nos. 807 and 807-A and FERC’s regulations at 18 C.F.R. §§ 35.28(d)(2)(ii)(A)-(B) with respect to excess or unused capacity on Successful Bidder’s ICIF, including Successful Bidder’s rebuttable presumption to a “safe harbor” and associated priority rights.  In entering into the PPA, Distribution Company is relying on the agreements made by Successful Bidder herein; provided, however, that breach of or default on this Commitment Agreement will not operate to create a breach of or default on the PPA, unless the conduct producing the breach or default of this Commitment Agreement would independently create a breach or default of such PPA.

- Successful Bidder shall file this Commitment Agreement, as well as any Voluntary Agreement concluded pursuant to it, with FERC for acceptance pursuant to FPA Section 205.

[Signature Page Follows]

IN WITNESS WHEREOF, Successful Bidder has caused this Commitment Agreement to be duly executed on its behalf as of the date first above written.

[SUCCESSFUL BIDDER’S NAME]

By:_________________________________

Name:

Title:

Signature Page to 
Voluntary Agreement Commitment Agreement

This draft Offshore Wind Power Purchase Agreement is intended to provide a general description of the terms to which the electric distribution companies are willing to agree.  Bidders are discouraged from proposing any material changes or conditions to the draft Agreement, and the electric distribution companies have no obligation to accept any specific proposed changes or conditions.  The final Agreement will be subject to negotiations with the individual electric distribution companies and will be customized to address the relevant circumstances.  Accordingly, certain provisions in the final Agreement may differ from this draft Agreement.

NTD:  This date must be no later than four years after the Guaranteed Commercial Operation Date included in Section 3.1(a)(viii).

NTD:  As described in Section 2.2.2.11 of the RFP, if a project is being developed in phases and under separate contracts, additional security equal to $37,500/MW per contract shall be required to secure the completion of both phases to be provided at commercial operation of the first phase of the project. Moreover, it is assumed that the Related Transmission Facilities and Network Upgrades for both phases would be completed by the Commercial Operation Date of the first facility to achieve that date.

Open Access and Priority Rights on Interconnection Customer’s Interconnection Facilities, 150 FERC ¶ 61,211 (“Order No. 807”), order on reh’g. 153 FERC ¶ 61,047 (“Order No. 807-A) (2015).